## Summary Sheet for Release versi
cQube Release Version - 1.1 TestScript Execution Summary Sheet
Planned Start Date | Actual Start Date | Test Name | Environment of Test Activity | Type of testing Manual / Automation | Total Number of Tests planned | Total number of Test cases / Scripts prepared | Number Of Test Cases Executed | Total Number Of Test Cases Got Passed | Total Number Of Test Cases Got Failed/Errors | Resolved Defects | Pass % | Fail %
2020-06-12 | 2020-06-12 | Nifi Duplicate records Validation | Testing Environment | Manual | 14 | 14 | 14 | 12 | 0 | 2 | 85.71% | 0%
2020-06-15 | 2020-06-17 | Nifi Process Grouping | Testing Environment | Manual | 30 | 30 | 30 | 26 | 0 | 4 | 86.67% | 0%
2020-06-16 | 2020-06-18 | Infra reports - Scatter plot | Testing Environment | Automation | 33 | 33 | 33 | 24 | 0 | 9 | 72.73% | 0%
2020-06-17 | 2020-06-17 | Infra report - Map Report | Testing Environment | Manual & Automation | 55 | 55 | 55 | 50 | 0 | 5 | 90.91% | 0%
2020-06-19 | 2020-06-20 | CRC report | Testing Environment | Automation | 27 | 27 | 27 | 24 | 0 | 3 | 88.89% | 0%
2020-06-22 | 2020-06-30 | graffana dashboard | Testing Environment | Manual | 15 | 15 | 15 | 11 | 0 | 4 | 73.33% | 0%
2020-07-08 | 2020-07-08 | Admin screens functional | Testing Environment | Automation | 40 | 40 | 40 | 38 | 0 | 2 | 95% | 0%
Release Testing
2020-07-07 | 2020-07-07 | Functional Testing | Test environment | Automation | 81 | 81 | 81 | 79 | 0 | 2 | 97.53% | 0%
2020-08-07 | 2020-08-07 | Regression Testing - Login, Student Attendance, Semester | Test environment | Automation | 60 | 60 | 60 | 58 | 0 | 2 | 96.67% | 0%
2020-07-08 | 2020-08-07 | Regression Testing - CRC, Infrastructure Map & Scatter plot | Test environment | Automation | 90 | 90 | 90 | 89 | 0 | 1 | 98.89% | 0%
2020-07-14 | 14/07/2020 | Load Test | Test environment | JMeter Test | 15 | 15 | 15 | 5 | 10 | 0 | 33.33% | 66.67%
2020-07-16 | 16/07/2020 | Smoke & Sanity Test | Release Environment | Automation | 76 | 76 | 76 | 76 | 0 | 0 | 100% | 0%

## Defects
cQube
Project Name | cQube 1.1
Report Name | Defects
Test Type | Manual & Automation
Created By | Devaraja & Chethan
Creation Date | 6/12/2020
Reviewed By
Reviewed Date
Defect Id | Functional Area | Defect Description | severity | status | Jira Link
TC_cQube_Nifi_validation_11 | Nifi duplicate validation | If the duplicate records containing the same id and same name But containing different lat long details. | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-372
TC_cQube_Nifi_validation_14 | Nifi duplicate validation | Check whether count calculation is working properly or not in log file | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-372
16/06/2020
1 | School InfraStructure Map Based Report | Click on Schools and check whether each dots on the map Contains Details, school infrastructure metrics % and other metrics. | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-371
2 | School InfraStructure Map Based Report | Click on Gujarath hyper link, Blocks, Clusters and Schools and check Whether number of schools are equivalent in all the clicks | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-371
3 | School InfraStructure Map Based Report | Click on clusters button, Map is not loading (Only loader is loading) | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-371
17/06/2020
1 | School InfraStructure Map Based Report - | Selected cluster's map is not loading Steps to re-produce: Goto given below district , block and cluster , issue that map is not loading Devbhomi dwarak --> Bhanavad --> Gunda Taluka shala Amreli --> Khambha --> Trakuda Pri.School Anand --> Borsad --> Kanbha Anand --> Khambhat --> Daheda Primary School Anand --> Khambhat --> Nagra Kumar Shala Banaskantha --> Amirgadh --> Sarotra Banaskantha --> Danta --> Sembalpani | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-371
18/06/2020
1 | School InfraStructure Scattor plot Report | Goto District select box , district names are not in orderwise | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
2 | School InfraStructure Scattor plot Report | Goto Table , Average % is wrong , % should be less than 100 but table shows more then 100% | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
3 | School InfraStructure Scattor plot Report | Select district as Jamnagar , select blocks , No data found issue Jamnagar --> Jamjodhapur Jamnagar --> Jamnagar Jamnagar --> Jodiya Jamnagar --> Kalavada Jamnagar --> Lalpura | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
4 | School InfraStructure Scattor plot Report | Select district as Porbandar , select blocks , table data is loading but but no data found on table i.e Porbandhar --> all blocks | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
5 | School InfraStructure Scattor plot Report | Select district as Junadhan , select blocks , table data is not loading but but no data found on table i.e Junadhan -->junadhan | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
6 | School InfraStructure Scattor plot Report | Select district as Surendranagar , select blocks , table data is loading but but no data found on table i.e Surendranagar --> all blocks | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
7 | School InfraStructure Scattor plot Report | Select district as Devbhoomi Dwaraka , choose blocks such as DevBhomi --> Dwaraka DevBhomi --> Jamkalyanapur DevBhomi --> Jamkhambhaliya table data is loading but no data found on table | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-370
19/06/2020
Tc_cQube_Nifi_Batch_Mode_006 | Nifi Batch Processing | Student Attendance template is showing Data flow error | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-411
Tc_cQube_Nifi_Batch_Mode_007 | Nifi Batch Processing | Crc template is showing Stopped componets 2 | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-412
Tc_cQube_Nifi_Batch_Mode_008 | Nifi Batch Processing | semester template is showing Invalid componets 11 | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-413
Tc_cQube_Nifi_Batch_Mode_009 | Nifi Batch Processing | static data template is showing Stopped componets 12 | Major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-414
20/06/2020
Tc_cQube_CRC_Report_007 | CRC Report | Check performance for school wise report download File is downloading but takes time around 30 sec | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-415
23/06/2020
Tc_cQube_Infrastructure_Report_015 | School infrastructure scattor report | Goto donwload report select box , choose school wise csv and click on download issue: downloading of school wise csv is taking more then one minute | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-416
24/06/2020
Tc_cQube_CRC_Report_016 | CRC Report | Select district from select box , select block from select box and select cluster from select box and check with table data is not loading , shows message as "No data found" i.e Valsad/ Vapi/ Vapi Valsad/ Valsad/ Dived Valsad/ Valsad/ Dungri Valsad/ Valsad/ Gorgam Valsad/ Valsad/ Faldhara Valsad/ Valsad/ Gorgam Valsad/ Valsad/ Navera Valsad/ Umbergaon/ Fansa Valsad/ Pardi/ Rentlav Valsad/ Pardi/ Sonwada Valsad/ Pardi/ Sukhesh Vadodara/ Padra/ Dabhasa | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-415
30/06/2020
TC_cQube_admin_login_010 | Admin login separation | Issue description : Admin login page only admin can have access but i have created dashboard report viewer , he also able to login to admin page | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-417
Grafana
Tc_cQube_Grafana_010 | Grafana Dashboard | Emit some data files to the s3 emission bucket Check whether total files emitted to s3 emission bucket is equivalent to the total files input on the grafana dashboard | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_011 | Grafana Dashboard | Emit some data files to the s3 emission bucket Check whether total files processed in the nifi are equivalent to the data which is showing on the grafana dashboard. (Total records processed) | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_012 | Grafana Dashboard | Emit some data files to the s3 emission bucket. Check whether total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_013 | Grafana Dashboard | Emit some data files to the s3 emission bucket Check whether total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. (Total records processed ) | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-418
2020-07-07
1 | Student Attendance | Choose any district and choose any block, Block name is showing undefined | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-419
2 | Student Attendance | Choose any district and choose any block, Block names are not showing in the select box | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-419
2020-07-08
Tc_cQube_Admin_Screen_025 | Admin screen | Postgres SQL Logs file is not downloaded | major | Resolved | https://project-sunbird.atlassian.net/browse/CQB-434
2020-07-09
Tc_cQube_Crc_Report_018 | CRC report | Selecting some blocks from select box , table is does not contain records it showing no data found , click on download button , it start downloading existing block records not select block record | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-415
TC_cQube_School_Map_060 | School infrastructure map report | Goto school infrastructure map report , check with footer value schools count is 20189, if click on blocks and school button school count is same , but different in when click on cluster button | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-433
14/09/2020
Tc_cQube_Regression_Sc_Report_142 | School infrastructure scatter plot | Cluster level table data is loaded but there is no data on table . displayed message as "No data found" i.e Dohad Zalod Sarori no data found! Dohad Sanjeli Limdi no data found! | Minor | Resolved | https://project-sunbird.atlassian.net/browse/CQB-436

## Nifi Duplicate Record Validatio
cQube 1.1
Project Name | cQube 1.1
Module Name | Nifi duplicate records validation
Test type | Manual
Created By | Devaraj
Creation Date | 2020-06-12
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
TC_cQube_Nifi_validation_01 | Check whether data files are loaded into the Nifi process from S3 input bucket | Data files must be loaded form s3 input bucket to nifi process. | same as expected | Pass
TC_cQube_Nifi_validation_02 | Check whether nifi read all the records from the data files. | Nifi should read the all the records from data files. | same as expected | Pass
TC_cQube_Nifi_validation_03 | Check whether nifi performs the validation or not by writing a grouping query. | Nifi should perform validation. | same as expected | Pass
TC_cQube_Nifi_validation_04 | Check the output without duplicates . | Nifi should fetch the files from s3 input bucket and records should be inserted into table. | same as expected | Pass
TC_cQube_Nifi_validation_05 | Check whether nifi performs validation on Duplicate records 1.copy the first two records in the file and paste it below the third Record. | Nifi should perform validation and duplicate records must be eliminated. | same as expected | Pass
TC_cQube_Nifi_validation_06 | Check which duplicate records will nifi eliminate from the file 1.Manually make some duplicate records as mirror image records. | One record should be considered and rest of the duplicate records should eliminate. | same as expected | Pass
TC_cQube_Nifi_validation_07 | Check whether nifi eliminate same id with different values in the file. | Nifi should eliminate both the records. | same as expected | Pass
TC_cQube_Nifi_validation_08 | Check whether nifi processes the records which are having the same id, Same name and different values. - Check the destination table containing id as a primary key | Nifi should eliminate both the records. | same as expected | Pass
TC_cQube_Nifi_validation_09 | Check whether Nifi performs blank line validation and store the blank lines count in the log_summnary table | Nifi should performs blank line validation and store the blank lines count in the log_summnary table | same as expected | Pass
TC_cQube_Nifi_validation_10 | Check whether nifi processes the records which are having the different id, Same name and same values. | Nifi should process and records should be inserted into table. | same as expected | Pass
TC_cQube_Nifi_validation_11 | Geo metric Duplication check -district, block, cluster and schools. If the duplicate records containing the same id and same name But containing different lat long details. | Nifi should elimiate both the records. | same as expected | Pass
TC_cQube_Nifi_validation_12 | Check whether nifi removes the records, where the records having null id's | Nifi should eliminate the those records. | same as expected | Pass
TC_cQube_Nifi_validation_13 | Check whether duplicate records are stored in the logs file. | Duplicate records should be stored in the log file. | same as expected | Pass
TC_cQube_Nifi_validation_14 | Check whether count calculation is working properly or not in log file | Count should match | same as expected | Pass

## Nifi Process Grouping
cQube 1.1
Project Name | cQube 1.1
Module Name | Nifi Batch Processing
Test type | Manual
Created By | Devaraj
Creation Date | 2020-06-17
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Tc_cQube_Nifi_Batch_Mode_001 | Check whether nifi successfully installed or not by ansible script | Niifi should be successfully installed and started | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_002 | Check whether Student Attendance template is successfully loaded or not While installing | Student attendance template must be loaded by ansible script while installing | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_003 | Check whether Crc template is successfully loaded or not While installing | Crc template must be loaded by ansible script while installing | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_004 | Check whether semester template is successfully loaded or not While installing | Semester template must be loaded by ansible script while installing | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_005 | Check whether static data template is successfully loaded or not While installing | Static data template must be loaded by ansible script while installing | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_006 | Check whether Student Attendance template is instantiated successfully and configured or not | Running Components should not be 0 ie Play Button(ex: 39), Stopped Components should be 0 ie.Square Button(ex:0), Invalid componenets should be 0 Ie .Triangle Button(ex:0) | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_007 | Check whether Crc template is instantiated successfully and configured or not | Running Components should not be 0 ie Play Button(ex: 39), Stopped Components should be 0 ie.Square Button(ex:0), Invalid componenets should be 0 Ie .Triangle Button(ex:0) | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_008 | Check whether semester template is instantiated successfully and configured or not | Running Components should not be 0 ie Play Button(ex: 39), Stopped Components should be 0 ie.Square Button(ex:0), Invalid componenets should be 0 Ie .Triangle Button(ex:0) | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_009 | Check whether static data template is instantiated successfully and configured or not | Running Components should not be 0 ie Play Button(ex: 39), Stopped Components should be 0 ie.Square Button(ex:0), Invalid componenets should be 0 Ie .Triangle Button(ex:0) | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_010 | Check whether Student Attendance template is able to disable and stop the Processor Manually | Student Attendance template must be stopped | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_011 | Check whether Crc template is able to disable and stop the Processor Manually | Crc template must be stopped | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_012 | Check whether Semester is able to disable and stop the Processor Manually | Semester template must be stopped | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_013 | Check whether Static data template is able to disable and stop the Processor Manually | Static data template must be stopped | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_014 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Click on Menu bar 3.Navigate to templates 4.Check whether student attendance, crc, semester and static data template Names are displayed or not | student attendance, crc, semester and static data template name should be displayed in the Nifi template section | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_015 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student attendance transformer 3.Right click on student_attendance_processor 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_016 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student attendance transformer 3.Right click on student_attendance_processor 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_017 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on crc processor 3.Right click on crc_processor 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_018 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on crc processor 3.Right click on crc_processor 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_019 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student semester transformer 3.Right click on student_semester_processor 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_020 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student semester transformer 3.Right click on student_semester_processor 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_021 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on static data transformer 3.Right click on static_data_processor 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_022 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on static_data_ transformer 3.Right click on static_data_processor 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_023 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student attendance transformer 3.Right click on cQube_raw_data_fetch_attendance Configuration 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_024 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student attendance transformer 3.Right click on cQube_raw_data_fetch_attendance Configuration 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_025 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on crc processor 3.Right click on cQube_raw_data_fetch_crc Configuration 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_026 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on crc processor 3.Right click on cQube_raw_data_fetch_crc Configuration 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_027 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student semester transformer 3.Right click on student_assessment_processor Configuration 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_028 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on student semester transformer 3.Right click on student_assessment_processor Configuration 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_029 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on static data transformer 3.Right click on cQube_raw_data_fetch_static Configuration 4. Goto configure 4.Check Process Group Name and Process Group Parameter Context are Configured or not | Process Group Name and Process Group Parameter Context must be configured | Same as Expected | Pass
Tc_cQube_Nifi_Batch_Mode_030 | 1.Enter url <http://<ip>:8096/nifi> on the search bar 2.Double click on static_data_ transformer 3.Right click on cQube_raw_data_fetch_static Configuration 4. Goto configure 4.Check whether all the controller-services are enabled or not | All the Controller -services must be enabled | Same as Expected | Pass

## Grafanna
Project Name | cQube 1.1
Module Name | Grafanna_Dashboard
Test type | Manual
Created By | Devaraja
Creation Date | 6/30/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Input data | Expected Result | Actual Result | Status
Tc_cQube_Grafana_001 | Check whether login page of grafana is displayed or not 1.Enter <ip:9000> | http://<ip>:9000/ | Grafana login page must be displayed | Same as expected | Pass
Tc_cQube_Grafana_002 | Check whether home page of grafana is displayed or not 1.Enter <ip:9000> 2.Enter valid username and password 3.Click on login | username: password: | Grafana home page must be displayed | Same as expected | Pass
Tc_cQube_Grafana_003 | Check whether cQube monitoring dashboard is displayed or not | http://<ip>:9000/ username: password: | cQube monitoring dashboard must be displayed | Same as expected | Pass
Tc_cQube_Grafana_004 | Check whether cpu utilization,memory usage,server-storage current,Nifi jvm heap memory used,Nifi-jvm heap usage,Total files and Total records graphs are displayed or not |  | Server-storage current,Nifi jvm heap memory used,Nifi-jvm heap usage, Total files nad Total records graphs must be displayed | Same as expected | Pass
Tc_cQube_Grafana_005 | Check whether cpu utilization (in percentage % ) of graph in the grafana is displaying proper data or not |  | Cpu utilization in the server is equaivalent to the data which is displaying on the grafana dashboard | Same as expected | Pass
Tc_cQube_Grafana_006 | Check whether memory usage (in percentage % ) of graph in the grafana is displaying proper data or not |  | Memory usage in the server is equaivalent to the data which is displaying on the grafana dashboard | Same as expected | Pass
Tc_cQube_Grafana_007 | Check whether sever-storage current(in %) of graph in the grafana is displaying proper data or not |  | Server storage in the server is equaivalent to the data which is displaying on the grafana dashboard | Same as expected | Pass
Tc_cQube_Grafana_008 | Check whether Nifi-jvm heap memory usage is displaying proper data or not |  | Nifi-jvm heap memory usage in the server is equaivalent to the data which is displaying on the grafana dashboard | Same as expected | Pass
Tc_cQube_Grafana_009 | Check whether Nifi-jvm heap memory usage(in percentage %) is displaying proper data or not |  | Nifi-jvm heap memory usage in the server is equaivalent to the data which is displaying on the grafana dashboard | Same as expected | Pass
Tc_cQube_Grafana_010 | Emit some data files to the s3 emission bucket Check whether total files emitted to s3 emission bucket is equivalent to the total files input on the grafana dashboard |  | Total files emitted to s3 emission bucket must be equivalent to the Total files input on the grafana dashboard | No Data showing on the grafana dashboard | Pass
Tc_cQube_Grafana_011 | Emit some data files to the s3 emission bucket Check whether total files processed in the nifi are equivalent to the data which is showing on the grafana dashboard. (Total records processed) |  | Total files processed in the nifi must be equivalent to the data which is showing on the grafana dashboard. (Total records processed) | No Data showing on the grafana dashboard | Pass
Tc_cQube_Grafana_012 | Emit some data files to the s3 emission bucket. Check whether total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard |  | Total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard | No Data showing on the grafana dashboard | Pass
Tc_cQube_Grafana_013 | Emit some data files to the s3 emission bucket Check whether total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. (Total records processed ) |  | Total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. (Total records processed ) | No Data showing on the grafana dashboard | Pass
Tc_cQube_Grafana_014 | Check the total files section of grafana dashboard without emitting the data to the s3 emission bucket |  | No data must be displayed | Same as expected | Pass
Tc_cQube_Grafana_015 | Check the total records section of grafana dashboard without emitting the data to the s3 emission bucket |  | No data must be displayed | Same as expected | Pass

## Load Testing
Project Name | cQube 1.1
Module Name | Load Testing
Test type | JMeter test
Created By | Devaraja
Creation Date | 7/9/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Number Of Users | Status | Average Total Min Response Time | Average Total Max Response Time
Tc_cQube_Load_001 | 1.Login to cQube application. 2.Navigate to student attendance report. 3.Click on schools 4.Check the respose time with different users | 300 | Fail | 1sec | 73.749sec
|  | 270 | Fail | 2.14sec | 74.241sec
|  | 250 | Pass | 3.0sec | 65.889sec
Tc_cQube_Load_002 | 1.Login to cQube application. 2.Navigate to Crc report. 3.Click on schools 4.Check the respose time with different users | 200 | Fail | 3.8sec | 102.0sec
|  | 150 | Fail | 2.154sec | 89.296sec
|  | 100 | Pass | 1.2sec | 66.00sec
Tc_cQube_Load_003 | 1.Login to cQube application. 2.Navigate to semester. 3.Click on schools 4.Check the respose time with different users | 200 | Fail | 2.632sec | 77.422sec
|  | 170 | Fail | 3.7sec | 64.018sec
|  | 100 | Pass | 1.6sec | 39.15sec
Tc_cQube_Load_004 | 1.Login to cQube application. 2.Navigate to school infrastructure map report. 3.Click on schools 4.Check the respose time with different users | 300 | Fail | 2.2sec | 108.255sec
|  | 250 | Fail | 0.8sec | 92.381sec
|  | 200 | Pass | 1.1sec | 86.448sec
Tc_cQube_Load_005 | 1.Login to cQube application. 2.Navigate to school infrastructure report. 3.Click on schools 4.Check the respose time with different users | 200 | Fail | 0.6sec | 123.248sec
|  | 150 | Fail | 1.2sec | 94.716sec
|  | 100 | Pass | 0.941sec | 77.842sec

## Admin_Screen
cQube
Project Name | cQube 1.1
Module Name | Admin_Screen
Test Type | Automation
Created By | Chetan & Devaraja
Creation Date | 07/08/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Test Data | Expected Result | Actual Result | Status
Automation Testcases
Tc_cQube_Admin_Screen_001 | Check weather admin login page is displayed or not through vpn based port |  | Admin login should be display | Same as expected | Pass
Tc_cQube_Admin_Screen_002 | Check weather admin is login through admin login page | Valid email & Valid password | Admin should be login to admin user page | Same as expected | Pass
Tc_cQube_Admin_Screen_003 | Login to admin user , check weather only create user and chage password options are present or not |  | Create user and change password should be display in screen | Same as expected | Pass
Tc_cQube_Admin_Screen_004 | Check weather admin is able to create new user or not |  | New user is create and green message should be display | Same as expected | Pass
Tc_cQube_Admin_Screen_005 | Check weather change password is working or not | Enter new password and Enter conf password | Password should be change | Same as expected | Pass
Tc_cQube_Admin_Screen_006 | Login to admin page again , check new password is working or not | Valid email & new password | Login to admin page | Same as expected | Pass
Tc_cQube_Admin_Screen_007 | Create admin role |  | Admin role to be should created | Same as expected | Pass
Tc_cQube_Admin_Screen_008 | Create dashboard report viewer |  | Dashboard report viewer should be create | Same as expected | Pass
Tc_cQube_Admin_Screen_009 | Check newly created admin user in vpn based |  | Admin should be logined and create user and change password should be present | Same as expected | Pass
Tc_cQube_Admin_Screen_010 | Check newly created dashboard report viewer is should not login to vpn based |  | Vpn based admin login should be not allow to dashboard report viewer to login | Same as expected | Pass
Tc_cQube_Admin_Screen_011 | Check newly created dashboard report viewer is logined to cqube application and check in dashboard contains change password button is present or not |  | Dashboard report viewer should be logined to cqube application | Same as expected | Pass
Tc_cQube_Admin_Screen_012 | Goto logs , choose log type as Application and select log name as node info logs and check wether file is downloading or not |  | Node info log csv file should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_013 | Goto logs , choose log type as Application and select log name as node error logs and check wether file is downloading or not |  | Node info error csv file should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_014 | Goto logs , choose log type as Application and select log name as angular info logs and check wether file is downloading or not |  | Angular info log should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_015 | Goto logs , choose log type as Application and select log name as angular error logs and check wether file is downloading or not |  | Angular error log should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_016 | Goto logs , choose log type as Admin and select log name as node info logs and check wether file is downloading or not |  | Node info log csv file should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_017 | Goto logs , choose log type as admin and select log name as node error logs and check wether file is downloading or not |  | Node info error csv file should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_018 | Goto logs , choose log type as admin and select log name as angular info logs and check wether file is downloading or not |  | Angular info log should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_019 | Goto logs , choose log type as admin and select log name as angular error logs and check wether file is downloading or not |  | Angular error log should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_020 | Goto logs , choose log type as nifi and select log name as app logs and check wether file is downloading or not |  | App logs file should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_021 | Goto logs , choose log type as nifi and select log name as Bootstrap logs and check wether file is downloading or not |  | Bootstrap logs should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_022 | Goto logs , choose log type as python and select log name as access logs and check wether file is downloading or not |  | Access log should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_023 | Goto logs , choose log type as python and select log name as error logs and check wether file is downloading or not |  | Error logs should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_024 | Goto logs , choose log type as System and select log name as system logs and check wether file is downloading or not |  | System logs should be download | Same as expected | Pass
Tc_cQube_Admin_Screen_025 | Goto logs , choose log type as postgres and select log name as postgress and check wether file is downloading or not |  | Postgress sql logs should be download | Postgres SQL Logs file is not downloaded | Pass
Tc_cQube_Admin_Screen_026 | Goto Dashboard of cQube dashboard , click on all Users and check weather navigated to all users page or not |  | User's list should be display | Same as expected | Pass
Tc_cQube_Admin_Screen_027 | Goto user list page , click on table swap icons and check ascending or descending orderwise is working or not |  | Table should be change order once click on table swap icons | Same as expected | Pass
Tc_cQube_Admin_Screen_028 | Goto userlist page , click on Activated button , check weather working or not |  | Activate button should show pop box once click on it | Same as expected | Pass
Tc_cQube_Admin_Screen_029 | Goto userlist page , click on newly created user Activated button , and click ok on deactivate pop notification and check status is changed or not |  | Status should be change | Status should not changing | Pass
Tc_cQube_Admin_Screen_030 | Goto userlist page , click on Deactivate button , and click ok on activate pop notification and check status is changed or not |  | Status should be change | Same as expected | Pass
Tc_cQube_Admin_Screen_031 | Goto userlist table check with name data , it shoud not contain null in there in name |  | Names should not be contains name with null | Same as expected | Pass
Tc_cQube_Admin_Screen_032 | Goto cQube dashboard , click on S3 file download and check weather working or not |  | S3 files download page should be display | Same as expected | Pass
Tc_cQube_Admin_Screen_033 | Goto S3 file download page , check weather select drop down options are selectble or not |  | Select dropdown options should be selectable | Same as expected | Pass
Tc_cQube_Admin_Screen_034 | Goto S3 file download page ,select each dropdown and choose file and click on download and check weather file downloading or not |  | Selected file should be downloaded | Same as expected | Pass
Tc_cQube_Admin_Screen_035 | Goto admin login landing page, click on all icons and check weather working or not |  | All icons should be navigate to there page | Same as expected | Pass
Tc_cQube_Admin_Screen_036 | click on logout button and check weather logout is working or not |  | Navigate back to admin login page | Same as expected | Pass
Tc_cQube_Admin_Screen_037 | Goto admin login page ,click on each dashboard icons |  | Dashboard icons should be clickable | Same as expected | Pass
Tc_cQube_Admin_Screen_038 | Create user and check weather creater user is present in all user list or not |  | Newly created user should be present in all user list | Same as expected | Pass
Tc_cQube_Admin_Screen_039 | Goto to all users , check with search box is working or not |  | Search box should be work | Same as expected | Pass
Tc_cQube_Admin_Screen_040 | Click on monitoring details icons , check weather it is navigated to grafana dashboard or not |  | Navigated to grafana dashboard shouldbe display | Same as expected | Pass

## CRC Report
Project Name | cQube 1.1
Module Name | CRC_Performance
Test type | Automation
Created By | Chetan & Devaraj
Creation Date | 6/19/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Automation Test Cases
Tc_cQube_Crc_Report_001 | Check whether dashboad menu of cqube is working or not | Menu list should be Open | Same as expected | Pass
Tc_cQube_Crc_Report_002 | Check whether dashboad menu of CRC Report is working or not | Crc report for: Gujarat Should display | Same as expected | Pass
Tc_cQube_Crc_Report_003 | Check performance of crc report Goto Dashboard menu , click on crc report and check weather crc report is loaded within 5 sec or not | Crc report must be loaded in within 5 sec | Same as expected | Pass
Tc_cQube_Crc_Report_004 | Check performance for district wise report download | District wise csv should be downloaded within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_005 | Check performance for block wise report download | Block wise csv should be downloaded within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_006 | Check performance for cluster wise report download | Cluster wise csv should be download within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_007 | Check performance for school wise report download | School wise csv should be download within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_008 | Check performance for choose district , choose block and choose cluster from select box and check weather table data is loading or not within specified time | Table data should load within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_009 | Download the block wise csv and check downloading or not | Blockwise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_010 | Download the cluster wise csv and check downloading or not | Cluster wise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_011 | Download the school wise csv and check downloading or not | School wise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_012 | Check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
Tc_cQube_Crc_Report_013 | Select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_014 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_015 | Select district from select box ,select block from select box ,select cluster from select box click on download icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_016 | Select district from select box , select block from select box and select cluster from select box and check with table data is loading or not | School level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_017 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_018 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_019 | Check with logout functionality | Navigate back to login page | Same as expected | Pass
Tc_cQube_Crc_Report_020 | Check with x and y axis values are selectable or not | Both x and y axis values should be sele -ctable | Same as expected | Pass
Tc_cQube_Crc_Report_021 | Check with districtwise total no of schools details | District wise no of school value is should be same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_022 | Check with districtwise total no of schools visited | District wise no of school visited value is should same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_023 | Check with districtwise total no of schools visits | District wise no of school visites value is should same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_024 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
Tc_cQube_Crc_Report_025 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
Tc_cQube_Crc_Report_026 | Select district,block and cluster and click on home icon | Navigated to crc report | Same as expected | Pass
Tc_cQube_Crc_Report_027 | Check on crc report and click on logout | Login page should be displayed | Same as expected | Pass

## School Infrastructure Map Repor
cQube 1.1
Project Name | cQube 1.1
Module Name | School Infrastructure Map Based Report
Test type | Manual And Automation
Created By | Chetan & Devaraj
Creation Date | 6/16/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Manual Test Cases
Tc_cQube_School_Infra_001 | Click on gujarath hyper link and check whether each dots on the map Contains Details, school infrastructure metrics % and other metrics | All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information | Same as expected | Pass
Tc_cQube_School_Infra_002 | Click on Blocks and check whether check whether each dots on the map Contains Details, school infrastructure metrics % and other metrics. | All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information | Same as expected | Pass
Tc_cQube_School_Infra_003 | Click on Clusters and check whether check whether each dots on the map Contains Details, school infrastructure metrics % and other metrics. | All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information | Same as expected | Pass
Tc_cQube_School_Infra_004 | Click on Schools and check whether check whether each dots on the map Contains Details, school infrastructure metrics % and other metrics. | All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information | Same as expected | Pass
Tc_cQube_School_Infra_005 | Select school_infra from select box and check whether infrastructure_score is Highligted on the markers | Infrastructure_score should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_006 | Select boy’s toilet from select box and check whether infrastructure_score is Highligted on the markers | Boy’s toilet should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_007 | Select drinking water from select box and check whether infrastructure_score is Highligted on the markers | Drinking water should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_008 | Select electricity from select box and check whether infrastructure_score is Highligted on the markers | Electricity should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_009 | Select girl’s toilet from select box and check whether infrastructure_score is Highligted on the markers | Girl’s toilet should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_010 | Select hand pump’s from select box and check whether infrastructure_score is Highligted on the markers | Hand pump’s should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_011 | Select hand wash from select box and check whether infrastructure_score is Highligted on the markers | Hand wash should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_012 | Select library from select box and check whether infrastructure_score is Highligted on the markers | Library should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_013 | Select solar panel from select box and check whether infrastructure_score is Highligted on the markers | Solar panel should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_014 | Select tap water from select box and check whether infrastructure_score is Highligted on the markers | Tap water should be highlighted on the markers | Same as expected | Pass
Tc_cQube_School_Infra_015 | Select toilet’s from select box and check whether infrastructure_score is Highligted on the markers | Toilet’s should be highlighted on the markers | Same as expected | Pass
Automation Test Cases
Tc_cQube_School_Infra_016 | Check whether dashboad menu of cqube is working or not | Dashboard menu list to be display | Same as expected | Pass
Tc_cQube_School_Infra_017 | Check whether dashboad menu of School infrastructure is working or not | Navigate to School infrastructure Report | Same as expected | Pass
Tc_cQube_School_Infra_018 | Click on School infrastructure options , check weather options displayed or not | options should be display | Same as expected | Pass
Tc_cQube_School_Infra_019 | Goto Dashboard , click on school infrastructure , and click on Report(map) , Check weather is navigate to Report(map) or not | Navigate to Report(map) page should be display | Same as expected | Pass
Tc_cQube_School_Infra_020 | Check whether map is displayed or not On the school infra map based Report | Map should be display | Same as expected | Pass
Tc_cQube_School_Infra_021 | Check whether Points are displayed or not On the map | Points should be displayed on the map | Same as expected | Pass
Tc_cQube_School_Infra_022 | Click on Gujarat hyper link | It should be refresh school infrastructure page | Same as expected | Pass
Tc_cQube_School_Infra_023 | Click on Download icon and check weather csv file is downloading or not | Csv file is should be download once click on Download_icon | Same as expected | Pass
Tc_cQube_School_Infra_024 | Click on District select box and check weather select box contains options or Not | District select box should be display list of districts | Same as expected | Pass
Tc_cQube_School_Infra_025 | Select any District from select box , and check weather choosed district is selected Or not | District record should be display of selected district | Same as expected | Pass
Tc_cQube_School_Infra_026 | Select any District from select box ,select any block from select box and check Weather block is selected or not | block record should be display of selected block | Same as expected | Pass
Tc_cQube_School_Infra_027 | Select any District from select box ,select any block from select box and choose Any cluster name from select box | Cluster record should be display of selected cluster | Same as expected | Pass
Tc_cQube_School_Infra_028 | Select any district from select box and click on download button to check it is Downloading or not | Download the selected districtwise csv file | Same as expected | Pass
Tc_cQube_School_Infra_029 | Select any district from select box and select any block from select box click on donwload button to check weather its downloading or not | Download the selected Blockwise csv file | Same as expected | Pass
Tc_cQube_School_Infra_030 | Select any district from select box and select any block from select box and Select Cluster from select box ,click on donwload button to check weather it is Downloading or not | Download the selected Clusterwise csv file | Same as expected | Pass
Tc_cQube_School_Infra_031 | Select any district from select box and click on Home icon check weather page is Navigated to school_infrastructure page or not | Navigate back to school infrastructure home page | Same as expected | Pass
Tc_cQube_School_Infra_032 | Click on logout button | Navigate back to login page of cQube application | Same as expected | Pass
Tc_cQube_School_Infra_033 | Click on Catories select box , check weather cataory list is displaying or not | List of catagories to be display | Same as expected | Pass
Tc_cQube_School_Infra_034 | select any option from Infra_scores select box , check in map tooltip should contains Selected option record | It should be display selected option record on tool tip of map | Same as expected | Pass
Tc_cQube_School_Infra_035 | Goto Infra_scores drop down and select as Infra_score | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_036 | Goto Infra_scores drop down and select as Handwash_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_037 | Goto Infra_scores drop down and select as Solar_panel_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_038 | Goto Infra_scores drop down and select as Library_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_039 | Goto Infra_scores drop down and select as Drinking_Water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_040 | Goto Infra_scores drop down and select as Tap_water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_041 | Goto Infra_scores drop down and select as Hand_Pumps_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_042 | Goto Infra_scores drop down and select as Electricity_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_043 | Goto Infra_scores drop down and select as Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_044 | Goto Infra_scores drop down and select as Boy’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_045 | Goto Infra_scores drop down and select as Girl’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
Tc_cQube_School_Infra_046 | Click on Blocks button , check weather block level map is displaying or not | Block level records should be display on map | Same as expected | Pass
Tc_cQube_School_Infra_047 | Click on Blocks button , check with footer informations | Block level footer information to be display | Same as expected | Pass
Tc_cQube_School_Infra_048 | Click on Blocks button , and click on download button | block level csv should be download | Same as expected | Pass
Tc_cQube_School_Infra_049 | Click on Clusters button , check weather block level map is displaying or not | Cluster level records should be display on map | Same as expected | Pass
Tc_cQube_School_Infra_050 | Click on Cluster button , check with footer informations | Cluster level footer information to be display | Same as expected | Pass
Tc_cQube_School_Infra_051 | Click on Clusters button , and click on download button | Cluster level csv should be download | Same as expected | Pass
Tc_cQube_School_Infra_052 | Click on Schools button , check weather block level map is displaying or not | School level records should be display on map | Same as expected | Pass
Tc_cQube_School_Infra_053 | Click on Schools button , and click on download button | School level footer information to be display | Same as expected | Pass
Tc_cQube_School_Infra_054 | Click on Schools button , check with footer informations | School level csv should be download | Same as expected | Pass
Tc_cQube_School_Infra_055 | Click on Gujarath hyper link, Blocks, Clusters and Schools and check Whether number of schools are equivalent in all the clicks" Number of schools should be equal for -Blocks -Clusters -Schools | Number of schools should be equal for each block , Cluster and school | Same as expected | Pass

## Infrastructure - Scattor Plot
Project Name | cQube 1.1
Module Name | School Infrastructure Report (Scattor plot)
Test type | Automation
Created By | Chetan & Devaraj
Creation Date | 6/18/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Automation Test Cases
Tc_cQube_Infrastructure_Report_001 | Check whether dashboad menu of cqube is working or not | Menu list should be Open | same as expected | Pass
Tc_cQube_Infrastructure_Report_002 | Check whether dashboad menu of School infrastructure report is working or not | School Infrastructure report for: Gujarat Should display | same as expected | Pass
Tc_cQube_Infrastructure_Report_003 | Check page contains Graph and Tables | Graph and table should be display | same as expected | Pass
Tc_cQube_Infrastructure_Report_004 | Select districtwise csv option from download report from select box and click on donwload icon | It should download the selected download report csv | Same as expected | Pass
Tc_cQube_Infrastructure_Report_005 | Select blockwise csv option from download report from select box and click on donwload icon | It should download the selected download report csv | Same as expected | Pass
Tc_cQube_Infrastructure_Report_006 | Select clusterwise csv option from download report from select box and click on donwload icon | It should download the selected download report csv | Same as expected | Pass
Tc_cQube_Infrastructure_Report_007 | Select schoolwise csv option from download report from select box and click on donwload icon | It should download the selected download report csv | Same as expected | Pass
Tc_cQube_Infrastructure_Report_008 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
Tc_cQube_Infrastructure_Report_009 | Check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
Tc_cQube_Infrastructure_Report_010 | Select district,block and click on home icon | Navigated to crc report | Same as expected | Pass
Tc_cQube_Infrastructure_Report_011 | Select district,block and cluster and click on home icon | Navigated to crc report | Same as expected | Pass
Tc_cQube_Infrastructure_Report_012 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
Tc_cQube_Infrastructure_Report_013 | Select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
Tc_cQube_Infrastructure_Report_014 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
Tc_cQube_Infrastructure_Report_015 | Select district from select box ,select block from select box ,select cluster from select box click on download -icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
Tc_cQube_Infrastructure_Report_016 | Select district from select box , select block from select box and select cluster from select box and check with table data is loading or not | School level table data should be display | Same as expected | Pass
Tc_cQube_Infrastructure_Report_017 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
Tc_cQube_Infrastructure_Report_018 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
Tc_cQube_Infrastructure_Report_019 | Goto district wise table data and check with metric percentages | Average metrics percentage should be below or equal 100% | Same as expected | Pass
Tc_cQube_Infrastructure_Report_020 | Goto District wise select box and check weather district names are in order wise or not | District names should be in orderwise | Same as expected | Pass
Tc_cQube_Infrastructure_Report_021 | Check with x and y axis values are selectable or not | Both x and y axis values should be sele -ctable | Same as expected | Pass
Tc_cQube_Infrastructure_Report_022 | Click on crc report and click on logout | Login page should be displayed | Same as expected | Pass
Tc_cQube_Infrastructure_Report_023 | Goto xaxis select box and check options are present or not | Xaxis options should be display | Same as expected | Pass
Tc_cQube_Infrastructure_Report_024 | Goto yaxis select box and check options are present or not | Yaxis options should be display | Same as expected | Pass

## Functional_Testcases
Project Name | cQube 1.1
Test Case Name | Functional_Testcases
Created By | Chetan & Devaraj
Creation Date | 7/7/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Automation Testcases
CRC Report
Tc_cQube_Crc_Report_001 | Check whether dashboad menu of cqube is working or not | Menu list should be Open | Same as expected | Pass
Tc_cQube_Crc_Report_002 | Check whether dashboad menu of CRC Report is working or not | CRC report for: Gujarat Should display | Same as expected | Pass
Tc_cQube_Crc_Report_003 | Check performance of crc report Goto Dashboard menu , click on crc report and check weather crc report is loaded within 5 sec or not | Crc report must be loaded in within 5 sec | Same as expected | Pass
Tc_cQube_Crc_Report_004 | Check performance for district wise report download | District wise csv should be downloaded within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_005 | Check performance for block wise report download | Block wise csv should be downloaded within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_006 | Check performance for cluster wise report download | Cluster wise csv should be download within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_007 | Check performance for school wise report download | School wise csv should be download within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_008 | Check performance for choose district , choose block and choose cluster from select box and check weather table data is loading or not within specified time | Table data should load within specified time | Same as expected | Pass
Tc_cQube_Crc_Report_009 | Download the block wise csv and check downloading or not | Blockwise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_010 | Download the cluster wise csv and check downloading or not | Cluster wise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_011 | Download the school wise csv and check downloading or not | School wise csv is should be download | Same as expected | Pass
Tc_cQube_Crc_Report_012 | Check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
Tc_cQube_Crc_Report_013 | Select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_014 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_015 | Select district from select box ,select block from select box ,select cluster from select box click on download -icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
Tc_cQube_Crc_Report_016 | Select district from select box , select block from select box and select cluster from select box and check with table data is loading or not | School level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_017 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_018 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
Tc_cQube_Crc_Report_019 | Check with logout functionality | Navigate back to login page | Same as expected | Pass
Tc_cQube_Crc_Report_020 | Check with x and y axis values are selectable or not | Both x and y axis values should be sele -ctable | Same as expected | Pass
Tc_cQube_Crc_Report_021 | Check with districtwise total no of schools details | District wise no of school value is should be same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_022 | Check with districtwise total no of schools visited | District wise no of school visited value is should same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_023 | Check with districtwise total no of schools visits | District wise no of school visites value is should same as in districtwise downloaded csv | Same as expected | Pass
Tc_cQube_Crc_Report_024 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
Tc_cQube_Crc_Report_025 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
Tc_cQube_Crc_Report_027 | Click on crc report and click on logout | Login page should be displayed | Same as expected | Pass
School infra Map
TC_cQube_School_Map_028 | Check whether dashboad menu of cqube is working or not | Dashboard menu list to be display | Same as expected | Pass
TC_cQube_School_Map_029 | Check whether dashboad menu of School infrastructure is working or not | Navigate to School infrastructure Report | Same as expected | Pass
TC_cQube_School_Map_030 | Click on School infrastructure options , check weather options displayed or not | Options should be display | Same as expected | Pass
TC_cQube_School_Map_031 | Goto Dashboard , click on school infrastructure , and click on Report(map) , Check weather is navigate to Report(map) or not | Navigate to Report(map) page should be display | Same as expected | Pass
TC_cQube_School_Map_032 | Check whether map is displayed or not On the Semester Report | Map should be display | Same as expected | Pass
TC_cQube_School_Map_033 | Check whether Points are displayed or not On the map | Points should be displayed on the map | Same as expected | Pass
TC_cQube_School_Map_034 | Click on Gujarat hyper link | It should be refresh school infrastructure page | Same as expected | Pass
TC_cQube_School_Map_035 | Click on Download icon and check weather csv file is downloading or not | Csv file is should be download once click on Download_icon | Same as expected | Pass
TC_cQube_School_Map_036 | Click on District select box and check weather select box contains options or Not | District select box should be display list of districts | Same as expected | Pass
TC_cQube_School_Map_037 | Select any district from select box and click on download button to check it is Downloading or not | Download the selected districtwise csv file | Same as expected | Pass
TC_cQube_School_Map_038 | Select any district from select box and select any block from select box click on donwload button to check weather its downloading or not | Download the selected Blockwise csv file | Same as expected | Pass
TC_cQube_School_Map_039 | Select any district from select box and select any block from select box and Select Cluster from select box ,click on donwload button to check weather it is Downloading or not | Download the selected Clusterwise csv file | Same as expected | Pass
TC_cQube_School_Map_040 | Select any district from select box and click on Home icon check weather page is Navigated to school_infrastructure page or not | Navigate back to school infrastructure home page | Same as expected | Pass
TC_cQube_School_Map_041 | Click on logout button | Navigate back to login page of cQube application | Same as expected | Pass
TC_cQube_School_Map_042 | Click on Catories select box , check weather cataory list is displaying or not | List of catagories to be display | Same as expected | Pass
TC_cQube_School_Map_043 | Select any option from Infra_scores select box , check in map tooltip should contains Selected option record | It should be display selected option record on tool tip of map | Same as expected | Pass
TC_cQube_School_Map_044 | Goto Infra_scores drop down and select as Infra_score | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_045 | Goto Infra_scores drop down and select as Handwash_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_046 | Goto Infra_scores drop down and select as Solar_panel_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_047 | Goto Infra_scores drop down and select as Library_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_048 | Goto Infra_scores drop down and select as Drinking_Water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_049 | Goto Infra_scores drop down and select as Tap_water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_050 | Goto Infra_scores drop down and select as Hand_Pumps_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_051 | Goto Infra_scores drop down and select as Electricity_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_052 | Goto Infra_scores drop down and select as Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_053 | Goto Infra_scores drop down and select as Boy’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_054 | Goto Infra_scores drop down and select as Girl’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
TC_cQube_School_Map_055 | Click on Blocks button , check weather block level map is displaying or not | Block level records should be display on map | Same as expected | Pass
TC_cQube_School_Map_056 | Click on Blocks button , check with footer informations | Block level footer information to be display | Same as expected | Pass
TC_cQube_School_Map_057 | Click on Cluster button , check with footer informations | Cluster level footer information to be display | Same as expected | Pass
TC_cQube_School_Map_058 | Click on Clusters button , and click on download button | Cluster level csv should be download | Same as expected | Pass
TC_cQube_School_Map_059 | Click on Schools button , check weather block level map is displaying or not | School level records should be display on map | Same as expected | Pass
TC_cQube_School_Map_060 | Click on Gujarath hyper link, Blocks, Clusters and Schools and check Whether number of schools are equivalent in all the clicks" Number of schools should be equal for -Blocks -Clusters -Schools | Number of schools should be equal for each block , Cluster and school | Cluster level no of school count is different from blocks and schools | Resolved
School infra Report
Tc_cQube_School_Report_061 | Check whether dashboad menu of cqube is working or not | Menu list should be Open | Same as expected | Pass
Tc_cQube_School_Report_062 | Check whether dashboad menu of School infrastructure report is working or not | School Infrastructure report for: Gujarat Should display | Same as expected | Pass
Tc_cQube_School_Report_063 | Check page contains Graph and Tables | Graph and table should be display | Same as expected | Pass
Tc_cQube_School_Report_064 | Select districtwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
Tc_cQube_School_Report_065 | Select blockwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
Tc_cQube_School_Report_066 | Select clusterwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
Tc_cQube_School_Report_067 | Select schoolwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
Tc_cQube_School_Report_068 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
Tc_cQube_School_Report_069 | Check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
Tc_cQube_School_Report_070 | Select district,block and click on home icon | Navigated to crc report | Same as expected | Pass
Tc_cQube_School_Report_071 | Select district,block and cluster and click on home icon | Navigated to crc report | Same as expected | Pass
Tc_cQube_School_Report_072 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
Tc_cQube_School_Report_073 | Select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
Tc_cQube_School_Report_074 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
Tc_cQube_School_Report_075 | Select district from select box ,select block from select box ,select cluster from select box click on download -icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
Tc_cQube_School_Report_076 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
Tc_cQube_School_Report_077 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
Tc_cQube_School_Report_078 | Goto District wise select box and check weather district names are in order wise or not | District names should be in orderwise | Same as expected | Pass
Tc_cQube_School_Report_079 | Click on crc report and click on logout | Login page should be displayed | Same as expected | Pass
Tc_cQube_School_Report_080 | Goto xaxis select box and check options are present or not | Xaxis options should be display | Same as expected | Pass
Tc_cQube_School_Report_081 | Goto yaxis select box and check options are present or not | Yaxis options should be display | Same as expected | Pass

## Regression_Testcases
Project Name | cQube 1.1
Test Case Name | Regression_Testcases
Created By | Chetan & Devaraj
Creation Date | 7/10/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Automation Testcases
Login
cQube_Regression_Login_001 | Login to cQube application with valid user name and valid password | Navigate to cQube landing page | Same as expected | Pass
cQube_Regression_Login_002 | Check login with invalid email id without password and click on login button | Error message should be display this is field required | Same as expected | Pass
cQube_Regression_Login_003 | Check login with invalid email id with invalid password and click on login button | Error message should be display user not found | Same as expected | Pass
cQube_Regression_Login_004 | Check with invalid password range below 4 character and click login button | User able see error message on screen as minimum 4 character for password field | Same as expected | Pass
cQube_Regression_Login_005 | Check with login without giving credentials | User able see error message on screen as this field is required | Same as expected | Pass
cQube_Regression_Login_006 | Go to login of cQube application , give valid email and invalid password and check with login button | User able see error message on screen | Same as expected | Pass
cQube_Regression_Login_007 | Go to login of cQube application , give invalid email and valid password and check with login button | User able see error message on screen | Same as expected | Pass
cQube_Regression_Login_008 | Login to cQube application with valid user name and valid password and click on logout button | Navigate back to login page | Same as expected | Pass
cQube_Regression_Login_009 | Login with valid email and valid passwords which validity of user expired | User unable to login to application , error message is should be display as validity of user is exceeded | Same as expected | Pass
cQube_Regression_Login_010 | Login with invalid email id without providing domain name with valid password | User able to see error message on screen as invalid emai address | Same as expected | Pass
cQube_Regression_Login_011 | Check login to application by email and password must be less than 4 character | User able see error message on screen | Same as expected | Pass
cQube_Regression_Login_012 | Enter valid email and valid password and click on login button , check dashboard options | Dashboard options should be display | Same as expected | Pass
cQube_Landing Page |  |  |  | Pass
cQube_Regression_Landing_page_013 | Login to cQube application , check weather navigated to landing page or not | After login , landing page should be display | Same as expected | Pass
cQube_Regression_Landing_page_014 | Click on student attendance report icon and check weather navigated to student attendance report or not | Navigate to student attendance home page | Same as expected | Pass
cQube_Regression_Landing_page_015 | Click on crc report icon and check weather navigated to crc report or not | Navigate to crc report home page | Same as expected | Pass
cQube_Regression_Landing_page_016 | Click on semester report icon and check weather navigated to semester report or not | Navigate to semester report home page | Same as expected | Pass
cQube_Regression_Landing_page_017 | Click on teacher attendance report icon and check weather navigated to teacher attendance report or not | Navigate to teacher attendance coming soon page | Same as expected | Pass
cQube_Regression_Landing_page_018 | Click on school infrastrure map report icon and check weather navigated to school infrastructure map report or not | Navigate to school infrastrure map report home page | Same as expected | Pass
cQube_Regression_Landing_page_019 | Click on school infrastrure scattor report icon and check weather navigated to school infrastructure scattor report or not | Navigate to school infrastrure scattor report home page | Same as expected | Pass
Student Attendance report
cQube_Regression_Student_020 | Goto Dashboard , Check whether dashboad menu of cqube is working or not | Side navigation bar should Opened | Same as expected | Pass
cQube_Regression_Student_021 | Goto Dashboard ,Check whether dashboad menu of Student Attendence Reports is working or not | Attendance report for gujarat Should display | Same as expected | Pass
cQube_Regression_Student_022 | Check whether Points are displayed or not On the map | Points should be displayed on the map | Same as expected | Pass
cQube_Regression_Student_023 | Check whether,total number of schools are equal or not by click on blocks,clusters and schools | Total number of schools must be equal by click on blocks,clusters and schools | Same as expected | Pass
cQube_Regression_Student_024 | Check whether,total number of students are equal or not by click on blocks,clusters and schools | Total number of students must be equal by click on blocks,clusters and schools | Same as expected | Pass
cQube_Regression_Student_025 | Check whether Block Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Student_026 | Check whether Cluster Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Student_027 | Check whether School Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Student_028 | Check whether Download Functionality is working or not | User Should able to see the Downloaded File | Same as expected | Pass
cQube_Regression_Student_029 | Check whether Block level csv file is downloading or not | Block level csv file should be download | Same as expected | Pass
cQube_Regression_Student_030 | Check whether cluster level csv file is downloading or not | Cluster level csv file should be download | Same as expected | Pass
cQube_Regression_Student_031 | Check whether school level csv file is downloading or not | School level csv file should be download | Same as expected | Pass
cQube_Regression_Student_032 | Check whether Each District is selectable or not From select box and also check whether Blocks-per-district-report is generating or not | Blocks-per-district csv file should be generated | Same as expected | Pass
cQube_Regression_Student_033 | Check whether Each block is selectable or not From select box and also check whether Cluster_per_block_report is generating or not | Cluster_per_block_report csv file should be generated | Same as expected | Pass
cQube_Regression_Student_034 | Check whether Each cluster is selectable or not From select box and also check whether School_per_cluster_report is generating or not | School_per_cluster_report csv file should be generated | Same as expected | Pass
cQube_Regression_Student_035 | Check whether Navigation Functionality Is working or not | Navigation should happens From cluster level to state level | Same as expected | Pass
cQube_Regression_Student_036 | Check whether Home button is working or not | Home button should worl | Same as expected | Pass
cQube_Regression_Student_037 | Check Date range by selecting year and month | Date range should be change according to selected year and month | Same as expected | Pass
cQube_Regression_Student_038 | Check Dots are present on the map or not by selecting districts,block and clusters | Dots must be present | Same as expected | Pass
cQube_Regression_Student_039 | Check whether Logout Functionality Is working or not | Login Page should be display | Same as expected | Pass
CRC Report
cQube_Regression_Crc_040 | Goto Dashboard ,check whether dashboad menu of cqube is working or not | Menu list should be Open | Same as expected | Pass
cQube_Regression_Crc_041 | Goto Dashboard Check whether dashboad menu of CRC Report is working or not | Crc report for: Gujarat Should display | Same as expected | Pass
cQube_Regression_Crc_042 | Goto Dashboard ,check performance of crc report Goto Dashboard menu , click on crc report and check weather crc report is loaded within 5 sec or not | Crc report must be loaded in within 5 sec | Same as expected | Pass
cQube_Regression_Crc_043 | Check performance for district wise report download | District wise csv should be downloaded within specified time | Same as expected | Pass
cQube_Regression_Crc_044 | Check performance for block wise report download | Block wise csv should be downloaded within specified time | Same as expected | Pass
cQube_Regression_Crc_045 | Check performance for cluster wise report download | Cluster wise csv should be download within specified time | Same as expected | Pass
cQube_Regression_Crc_046 | Check performance for school wise report download | School wise csv should be download within specified time | Same as expected | Pass
cQube_Regression_Crc_047 | Check performance for choose district , choose block and choose cluster from select box and check weather table data is loading or not within specified time | Table data should load within specified time | Same as expected | Pass
cQube_Regression_Crc_048 | Download the block wise csv and check downloading or not | Blockwise csv is should be download | Same as expected | Pass
cQube_Regression_Crc_049 | Download the cluster wise csv and check downloading or not | Cluster wise csv is should be download | Same as expected | Pass
cQube_Regression_Crc_050 | Download the school wise csv and check downloading or not | School wise csv is should be download | Same as expected | Pass
cQube_Regression_Crc_051 | Check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
cQube_Regression_Crc_052 | Select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
cQube_Regression_Crc_053 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
cQube_Regression_Crc_054 | Select district from select box ,select block from select box ,select cluster from select box click on download -icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
cQube_Regression_Crc_055 | Select district from select box , select block from select box and select cluster from select box and check with table data is loading or not | School level table data should be display | Same as expected | Pass
cQube_Regression_Crc_056 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
cQube_Regression_Crc_057 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
cQube_Regression_Crc_058 | Check with logout functionality | Navigate back to login page | Same as expected | Pass
cQube_Regression_Crc_059 | Check with x and y axis values are selectable or not | Both x and y axis values should be sele -ctable | Same as expected | Pass
cQube_Regression_Crc_060 | Check with districtwise total no of schools details | District wise no of school value is should be same as in districtwise downloaded csv | Same as expected | Pass
cQube_Regression_Crc_061 | Check with districtwise total no of schools visited | District wise no of school visited value is should same as in districtwise downloaded csv | Same as expected | Pass
cQube_Regression_Crc_062 | Check with districtwise total no of schools visits | District wise no of school visites value is should same as in districtwise downloaded csv | Same as expected | Pass
cQube_Regression_Crc_063 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
cQube_Regression_Crc_064 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
cQube_Regression_Crc_065 | Select district,block and cluster and click on home icon | Navigated to crc report | Same as expected | Pass
cQube_Regression_Crc_066 | Click on crc report and click on logout | Login page should be displayed | Same as expected | Pass
Semester Report
cQube_Regression_Semester_067 | Check whether dashboad menu of cqube is working or not | Side navigation bar should Opened | Same as expected | Pass
cQube_Regression_Semester_068 | Check whether dashboad menu of Student Attendence Reports is working or not | Attendance report for gujarat Should display | Same as expected | Pass
cQube_Regression_Semester_069 | Check whether Points are displayed or not On the map | Points should be displayed on the map | Same as expected | Pass
cQube_Regression_Semester_070 | Check whether,total number of schools are equal or not by click on blocks,clusters and schools | Total number of schools must be equal by click on blocks, clusters and schools | Same as expected | Pass
cQube_Regression_Semester_071 | Check whether,total number of students are equal or not by click on blocks,clusters and schools | Total number of students must be equal by click on blocks,clusters and schools | Same as expected | Pass
cQube_Regression_Semester_072 | Check whether Block Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Semester_073 | Check whether Cluster Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Semester_074 | Check whether School Functionality is working or not | Map should be display and Points Should be visible on map | Same as expected | Pass
cQube_Regression_Semester_075 | Check whether Download Functionality is working or not | User Should able to see the Downloaded File | Same as expected | Pass
cQube_Regression_Semester_076 | Check whether Block level csv file is downloading or not | Block level csv file should be download | Same as expected | Pass
cQube_Regression_Semester_077 | Check whether cluster level csv file is downloading or not | Cluster level csv file should be download | Same as expected | Pass
cQube_Regression_Semester_078 | Check whether school level csv file is downloading or not | School level csv file should be download | Same as expected | Pass
cQube_Regression_Semester_079 | Check whether Each District is selectable or not From select box and also check whether Blocks-per-district-report is generating or not | Blocks-per-district csv file should be generated | Same as expected | Pass
cQube_Regression_Semester_080 | Check whether Each block is selectable or not From select box and also check whether Cluster_per_block_report is generating or not | Cluster_per_block_report csv file should be generated | Same as expected | Pass
cQube_Regression_Semester_081 | Check whether Each cluster is selectable or not From select box and also check whether School_per_cluster_report is generating or not | School_per_cluster_report csv file should be generated | Same as expected | Pass
cQube_Regression_Semester_082 | Check whether Navigation Functionality Is working or not | Navigation should happens From cluster level to state level | Same as expected | Pass
cQube_Regression_Semester_083 | Check whether Home icon is working or not | Districtwise map should be display | Same as expected | Pass
cQube_Regression_Semester_084 | Check home button is working or not | Navigate to landing page | Same as expected | Pass
cQube_Regression_Semester_085 | Check Dots are present on the map or not by selecting districts,block and clusters | Dots must be present | Same as expected | Pass
cQube_Regression_Semester_086 | Check whether Logout Functionality Is working or not | Login Page should be display | Same as expected | Pass
School infra map
cQube_Regression_Sc_Map_087 | Check whether dashboad menu of cqube is working or not | Dashboard menu list to be display | Same as expected | Pass
cQube_Regression_Sc_Map_088 | Check whether dashboad menu of School infrastructure is working or not | Navigate to School infrastructure Report | Same as expected | Pass
cQube_Regression_Sc_Map_089 | Click on School infrastructure options , check weather options displayed or not | Options should be display | Same as expected | Pass
cQube_Regression_Sc_Map_090 | Goto Dashboard , click on school infrastructure , and click on Report(map) , Check weather is navigate to Report(map) or not | Navigate to Report(map) page should be display | Same as expected | Pass
cQube_Regression_Sc_Map_091 | Check whether map is displayed or not On the Semester Report | Map should be display | Same as expected | Pass
cQube_Regression_Sc_Map_092 | Check whether Points are displayed or not On the map | Points should be displayed on the map | Same as expected | Pass
cQube_Regression_Sc_Map_093 | Click on Gujarat hyper link | It should be refresh school infrastructure page | Same as expected | Pass
cQube_Regression_Sc_Map_094 | Click on Download icon and check weather csv file is downloading or not | Csv file is should be download | Same as expected | Pass
cQube_Regression_Sc_Map_095 | Click on District select box and check weather select box contains options or Not | District select box should be display list of districts | Same as expected | Pass
cQube_Regression_Sc_Map_096 | Select any district from select box and click on download button to check it is Downloading or not | Download the selected districtwise csv file | Same as expected | Pass
cQube_Regression_Sc_Map_097 | Select any district from select box and select any block from select box click on donwload button to check weather its downloading or not | Download the selected Blockwise csv file | Same as expected | Pass
cQube_Regression_Sc_Map_098 | Select any district from select box and select any block from select box and Select Cluster from select box ,click on donwload button to check weather it is Downloading or not | Download the selected Clusterwise csv file | Same as expected | Pass
cQube_Regression_Sc_Map_099 | Select any district from select box and click on Home icon check weather page is Navigated to school_infrastructure page or not | Navigate back to school infrastructure home page | Same as expected | Pass
cQube_Regression_Sc_Map_100 | Click on logout button | Navigate back to login page of cQube application | Same as expected | Pass
cQube_Regression_Sc_Map_101 | Click on Catories select box , check weather cataory list is displaying or not | List of catagories to be display | Same as expected | Pass
cQube_Regression_Sc_Map_102 | select any option from Infra_scores select box , check in map tooltip should contains Selected option record | It should be display selected option record on tool tip of map | Same as expected | Pass
cQube_Regression_Sc_Map_103 | Goto Infra_scores drop down and select as Infra_score | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_104 | Goto Infra_scores drop down and select as Handwash_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_105 | Goto Infra_scores drop down and select as Solar_panel_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_106 | Goto Infra_scores drop down and select as Library_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_107 | Goto Infra_scores drop down and select as Drinking_Water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_108 | Goto Infra_scores drop down and select as Tap_water_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_109 | Goto Infra_scores drop down and select as Hand_Pumps_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_110 | Goto Infra_scores drop down and select as Electricity_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_111 | Goto Infra_scores drop down and select as Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_112 | Goto Infra_scores drop down and select as Boy’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_113 | Goto Infra_scores drop down and select as Girl’s Toilet_Percentage | Map should be display selected Infra_score record | Same as expected | Pass
cQube_Regression_Sc_Map_114 | Click on Blocks button , check weather block level map is displaying or not | Block level records should be display on map | Same as expected | Pass
cQube_Regression_Sc_Map_115 | Click on Blocks button , check with footer informations | Block level footer information to be display | Same as expected | Pass
cQube_Regression_Sc_Map_116 | Click on Cluster button , check with footer informations | Cluster level footer information to be display | Same as expected | Pass
cQube_Regression_Sc_Map_117 | Click on Clusters button , and click on download button | Cluster level csv should be download | Same as expected | Pass
cQube_Regression_Sc_Map_118 | Click on Schools button , check weather block level map is displaying or not | School level records should be display on map | Same as expected | Pass
cQube_Regression_Sc_Map_119 | Click on Gujarath hyper link, Blocks, Clusters and Schools and check Whether number of schools are equivalent in all the clicks" Number of schools should be equal for -Blocks -Clusters -Schools | Number of schools should be equal for each block , Cluster and school | totol no of school value is different in cluster level , compare to blocks and schools | Resolved
cQube_Regression_Sc_Map_120 | Select district from select box , and check with downloading csv file , comapare footer values with records in downloaded csv file | Both footer values and records in csv should be equivalent | Same as expected | Pass
cQube_Regression_Sc_Map_121 | Select district from select box , choose block from select box , and check with downloading csv file , comapare footer values with records in downloaded csv file | Both footer values and records in csv should be equivalent | Same as expected | Pass
cQube_Regression_Sc_Map_122 | Select district from select box , choose block from select box , choose cluster from select box and check with downloading csv file , comapare footer values with records in downloaded csv file | Both footer values and records in csv should be equivalent | Same as expected | Pass
cQube_Regression_Sc_Map_123 | Goto school infra map report , click on Blocks button check with all infra scores options are displaying or not on map | Block level infra scores records should be display | Same as expected | Pass
cQube_Regression_Sc_Map_124 | Goto school infra map report , click on Clusters button check with all infra scores options are displaying or not on map | Cluster level infra scores records should be display | Same as expected | Pass
cQube_Regression_Sc_Map_125 | Goto school infra map report , click on School button check with all infra scores options are displaying or not on map | School level infra scores records should be display | Same as expected | Pass
cQube_Regression_Sc_Map_126 | choose any district . any block and cluster , check with hyper link is working or not , modify like if click on block hyper link cluster is goes off , if click on gujarath navigate to districtwise home page | navigated back to districtiwise map page | Same as expected | Pass
School infra Report
cQube_Regression_Sc_Report_127 | Check whether dashboad menu of cqube is working or not | Menu list should be Open | Same as expected | Pass
cQube_Regression_Sc_Report_128 | Check whether dashboad menu of School infrastructure report is working or not | School Infrastructure report for: Gujarat Should display | Same as expected | Pass
cQube_Regression_Sc_Report_129 | Check page contains Graph and Tables | Graph and table should be display | Same as expected | Pass
cQube_Regression_Sc_Report_130 | Select districtwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
cQube_Regression_Sc_Report_131 | Select blockwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
cQube_Regression_Sc_Report_132 | Select clusterwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
cQube_Regression_Sc_Report_133 | Select schoolwise csv option from download report from select box and click on donwload icon | It should download the selected Download report csv | Same as expected | Pass
cQube_Regression_Sc_Report_134 | Check hyperlinks are navigating back to the districtwise crc report | Hyperlinks should navigate to the crc report | Same as expected | Pass
cQube_Regression_Sc_Report_135 | check with home button is working or not | Navigate back to districtwise crc report page | Same as expected | Pass
cQube_Regression_Sc_Report_136 | Select district,block and click on home icon | Navigated to crc report | Same as expected | Pass
cQube_Regression_Sc_Report_137 | Select district,block and cluster and click on home icon | Navigated to crc report | Same as expected | Pass
cQube_Regression_Sc_Report_138 | Click on district name on the table and check whether ascending and descending functionality is working or not | District name should be sorted based on the input | Same as expected | Pass
cQube_Regression_Sc_Report_139 | select district from select box ,click on download icon check weather block level csv is downloading or not | Block level csv should be download | Same as expected | Pass
cQube_Regression_Sc_Report_140 | Select district from select box ,select block from select box ,click on download icon check weather cluster level csv is downloading or not | Cluster level csv should be download | Same as expected | Pass
cQube_Regression_Sc_Report_141 | Select district from select box ,select block from select box ,select cluster from select box click on download -icon check weather school level csv is downloading or not | School level csv should be download | Same as expected | Pass
cQube_Regression_Sc_Report_142 | Select district from select box , select block from select box and select cluster from select box and check with table data is loading or not | School level table data should be display | Some of cluster table data showing no data found | Resolved
cQube_Regression_Sc_Report_143 | Select district from select box , select block from select box and check with table data is loading or not | Cluster level table data should be display | Same as expected | Pass
cQube_Regression_Sc_Report_144 | Select district from select box , check with table data is loading or not | Block level table data should be display | Same as expected | Pass
cQube_Regression_Sc_Report_145 | Check district wise table data and check with metric percentages | Average metrics percentage should be below or equal 100% | Same as expected | Pass
cQube_Regression_Sc_Report_146 | Check District wise select box and check weather district names are in order wise or not | District names should be in orderwise | Same as expected | Pass
cQube_Regression_Sc_Report_147 | Check on crc report and click on logout | Login page should be displayed | Same as expected | Pass
cQube_Regression_Sc_Report_148 | Check xaxis select box and check options are present or not | X axis options should be display | Same as expected | Pass
cQube_Regression_Sc_Report_149 | Check yaxis select box and check options are present or not | Y axis options should be display | Same as expected | Pass
cQube_Regression_Sc_Report_150 | Select district from select box ,select block from select box and select cluster from select box and check with download csv file and comapare csv file data with table records | Both csv file records and table data should be equivalent | Same as expected | Pass

## Smoke Testing
Project Name | cQube 1.1
Test Case Name | Smoke_Testcases
Created By | Chetan & Devaraj
Creation Date | 7/15/2020
Reviewed By | Srinivas N & Radhika
Reviewed Date
Test Case ID | Test Case Description | Expected Result | Actual Result | Status
Automation Testcases
Login_to_cQube
Smoke_Tc_001 | Check login functionality is working or not | Login to cqube application | Same as expected | Pass
Landing Page
Smoke_Tc_002 | Click on student attendance report icon and check weather navigated to student attendance report or not | Navigate to student attendance home page | Same as expected | Pass
Smoke_Tc_003 | Click on crc report icon and check weather navigated to crc report or not | Navigate to crc report home page | Same as expected | Pass
Smoke_Tc_004 | Click on semester report icon and check weather navigated to semester report or not | Navigate to semester report home page | Same as expected | Pass
Smoke_Tc_005 | Click on teacher attendance report icon and check weather navigated to teacher attendance report or not | Navigate to teacher attendance coming soon page | Same as expected | Pass
Smoke_Tc_006 | Click on school infrastrure map report icon and check weather navigated to school infrastructure map report or not | Navigate to school infrastrure map report home page | Same as expected | Pass
Smoke_Tc_007 | Click on school infrastrure scattor report icon and check weather navigated to school infrastructure scattor report or not | Navigate to school infrastrure scattor report home page | Same as expected | Pass
Student Attendance Report
Smoke_Tc_008 | Click on dash and click on student attedance report , check weather student attendance landing page is displayeed or not | Student attendance report landing page should be display | Same as expected | Pass
Smoke_Tc_009 | Check weather block button functionality is working or not | Block button functionality should be work | Same as expected | Pass
Smoke_Tc_010 | Check weather cluster button functionality is working or not | Cluster button functionality should be work | Same as expected | Pass
Smoke_Tc_011 | Check weather school button functionality is working or not | School button functionality should be work | Same as expected | Pass
Smoke_Tc_012 | Choose district from select box , check weather district is selectable or not | District should be selectable from select box | Same as expected | Pass
Smoke_Tc_013 | Choose district from select box , choose block from select box check weather block is selectable or not | Block should be selectable from select box | Same as expected | Pass
Smoke_Tc_014 | Choose district from select box , choose block from select box and select cluster from select box ,check weather cluster is selectable or not | Cluster should be selectable from select box | Same as expected | Pass
Smoke_Tc_015 | Click on hyper link , check weather it is working or not | Hyper link should be work | Same as expected | Pass
Smoke_Tc_016 | Click on blocks , cluster and school button and check each contains equivalent no of school record | No of schools record should be same | Same as expected | Pass
Smoke_Tc_017 | Click on blocks , cluster and school button and check each contains equivalent no of students record | No of students record should be same | Same as expected | Pass
Smoke_Tc_018 | Check with download icon is working or not | Download functionality should be work | Same as expected | Pass
Smoke_Tc_019 | Click on home icon , check weather it is working or not | Home icon should be work | Same as expected | Pass
Smoke_Tc_020 | Check year select box and month wise select box , options are selectable or not | Both functinalities should be work | Same as expected | Pass
Smoke_Tc_021 | Check markers present on map or not | Markers should be display on map | Same as expected | Pass
Smoke_Tc_022 | Check logout functionality is working or not | Logout should be work | Same as expected | Pass
CRC Report
Smoke_Tc_023 | Click on CRC report on dashboard , check weather navigate to crc report landing page or not | Navigated to crc report landing page | Same as expected | Pass
Smoke_Tc_024 | Check x axis and y axis select box and check each options are selectable or not | Both x and y axis options should be selectable | Same as expected | Pass
Smoke_Tc_025 | Check hyper link is working or not | Hyper link should be work | Same as expected | Pass
Smoke_Tc_026 | Choose district from select box , check weather district is selectable or not | District should be selectable from select box | Same as expected | Pass
Smoke_Tc_027 | Choose district from select box , choose block from select box check weather block is selectable or not | Block should be selectable from select box | Same as expected | Pass
Smoke_Tc_028 | Choose district from select box , choose block from select box and select cluster from select box ,check weather cluster is selectable or not | Cluster should be selectable from select box | Same as expected | Pass
Smoke_Tc_029 | Check with table data contains records or not and order of the table data | Table should be display records | Same as expected | Pass
Smoke_Tc_030 | Check with donwload report options are working or not | Download report options should be work | Same as expected | Pass
Smoke_Tc_031 | Select districtwise report and click on donwload button | Districtwise csv should be download | Same as expected | Pass
Smoke_Tc_032 | Select any district from select box and click on home icon check weather home is working or not | Home button should be work | Same as expected | Pass
Smoke_Tc_033 | Download districtwisecsv and compare Total Number of schools | Total no of school should be same | Same as expected | Pass
Smoke_Tc_034 | Download districtwisecsv and compare Total Number of visits | Total Number of visits should be same | Same as expected | Pass
Smoke_Tc_035 | Download districtwisecsv and compare Total schools visited | Total schools visited should be same | Same as expected | Pass
Smoke_Tc_036 | Check logout button , weather is working or not | Logout should be work | Same as expected | Pass
Smoke_Tc_037 |  |  | Same as expected | Pass
Smoke_Tc_038 | Click on dashboard and click on Semester report , check weather Semester landing page is displayeed or not | Semester report landing page should be display | Same as expected | Pass
Smoke_Tc_039 | Check weather block button functionality is working or not | Block button functionality should be work | Same as expected | Pass
Smoke_Tc_040 | Check weather cluster button functionality is working or not | Cluster button functionality should be work | Same as expected | Pass
Smoke_Tc_041 | Check weather school button functionality is working or not | School button functionality should be work | Same as expected | Pass
Smoke_Tc_042 | Choose district from select box , check weather district is selectable or not | District should be selectable from select box | Same as expected | Pass
Smoke_Tc_043 | Choose district from select box , choose block from select box check weather block is selectable or not | Block should be selectable from select box | Same as expected | Pass
Smoke_Tc_044 | Choose district from select box , choose block from select box and select cluster from select box ,check weather cluster is selectable or not | Cluster should be selectable from select box | Same as expected | Pass
Smoke_Tc_045 | Click on hyper link , check weather it is working or not | Hyper link should be work | Same as expected | Pass
Smoke_Tc_046 | Click on blocks , cluster and school button and check each contains equivalent no of school record | No of schools record should be same | Same as expected | Pass
Smoke_Tc_047 | Click on blocks , cluster and school button and check each contains equivalent no of students record | No of students record should be same | Same as expected | Pass
Smoke_Tc_048 | Check with download icon is working or not | Download functionality should be work | Same as expected | Pass
Smoke_Tc_049 | Click on home icon , check weather it is working or not | Home icon should be work | Same as expected | Pass
Smoke_Tc_050 | Check markers present on map or not | Markers should be display on map | Same as expected | Pass
Smoke_Tc_051 | Check logout functionality is working or not | Logout should be work | Same as expected | Pass
School Infrastructure Map report
Smoke_Tc_052 | Click on dashboard and click on school infra report , click on Map based Report ,check weather map report landing page is displayeed or not | School infra map based report landing page should be display | Same as expected | Pass
Smoke_Tc_053 | Check weather block button functionality is working or not | Block button functionality should be work | Same as expected | Pass
Smoke_Tc_054 | Check weather cluster button functionality is working or not | Cluster button functionality should be work | Same as expected | Pass
Smoke_Tc_055 | Check weather school button functionality is working or not | School button functionality should be work | Same as expected | Pass
Smoke_Tc_056 | Choose district from select box , check weather district is selectable or not | District should be selectable from select box | Same as expected | Pass
Smoke_Tc_057 | Choose district from select box , choose block from select box check weather block is selectable or not | Block should be selectable from select box | Same as expected | Pass
Smoke_Tc_058 | Choose district from select box , choose block from select box and select cluster from select box ,check weather cluster is selectable or not | Cluster should be selectable from select box | Same as expected | Pass
Smoke_Tc_059 | Click on hyper link , check weather it is working or not | Hyper link should be work | Same as expected | Pass
Smoke_Tc_060 | Click on blocks , cluster and school button and check each contains equivalent no of school record | No of schools record should be same | Same as expected | Pass
Smoke_Tc_061 | Click on blocks , cluster and school button and check each contains equivalent no of students record | No of students record should be same | Same as expected | Pass
Smoke_Tc_062 | Check with download icon is working or not | Download functionality should be work | Same as expected | Pass
Smoke_Tc_063 | Click on home icon , check weather it is working or not | Home icon should be work | Same as expected | Pass
Smoke_Tc_064 | Check markers present on map or not | Markers should be display on map | Same as expected | Pass
Smoke_Tc_065 | Check infra scores select box and check weather each options are selectable or not | Infra scores options should be selectable | Same as expected | Pass
Smoke_Tc_066 | Check logout functionality is working or not | Logout should be work | Same as expected | Pass
School Infra Scattor report
Smoke_Tc_067 | Click on scool infra report on dashboard ,click on Repot , check weather navigate to scattor report landing page or not | Navigated to school infra scattor report landing page | Same as expected | Pass
Smoke_Tc_068 | Check x axis and y axis select box and check each options are selectable or not | Both x and y axis options should be selectable | Same as expected | Pass
Smoke_Tc_069 | Check hyper link is working or not | Hyper link should be work | Same as expected | Pass
Smoke_Tc_070 | Choose district from select box , check weather district is selectable or not | District should be selectable from select box | Same as expected | Pass
Smoke_Tc_071 | Choose district from select box , choose block from select box and select cluster from select box ,check weather cluster is selectable or not | Cluster should be selectable from select box | Same as expected | Pass
Smoke_Tc_072 | Check with table data contains records or not and order of the table data | Table should be display records | Same as expected | Pass
Smoke_Tc_073 | Check with donwload report options are working or not | Download report options should be work | Same as expected | Pass
Smoke_Tc_074 | Select districtwise report and click on donwload button | Districtwise csv should be download | Same as expected | Pass
Smoke_Tc_075 | Select any district from select box and click on home icon check weather home is working or not | Home button should be work | Same as expected | Pass
Smoke_Tc_076 | Download districtwisecsv and compare Total schools visited | Total schools visited should be same | Same as expected | Pass