## Summary Sheet for Release version-1.1
		cQube Release Version - 1.1 TestScript Execution Summary Sheet

Planned Start Date	Actual Start Date	Test Name	Environment of Test Activity	Type of testing / Manual / Automation	Total Number of Tests planned	Total number of Test cases / Scripts prepared	Number Of Test Cases Executed	Total Number Of Test Cases Got Passed	Total Number Of Test Cases Got Failed/Errors	Resolved Defects	Pass %	Fail %
12 June 2020	12 June 2020	Nifi Duplicate records Validation	Testing Environment	Manual	14	14	14	12	0	2	85.71%	0.00%
15 June 2020	17 June 2020	Nifi Process Grouping	Testing Environment	Manual	30	30	30	26	0	4	86.67%	0.00%
16 June 2020	18 June 2020	Infra reports - Scatter plot	Testing Environment	Automation	33	33	33	24	0	9	72.73%	0.00%
17 June 2020	17 June 2020	Infra report - Map Report	Testing Environment	Manual & Automation	55	55	55	50	0	5	90.91%	0.00%
19 June 2020	20 June 2020	CRC report	Testing Environment	Automation	27	27	27	24	0	3	88.89%	0.00%
22 June 2020	30 June 2020	graffana dashboard	Testing Environment	Manual	15	15	15	11	0	4	73.33%	0.00%
8 July 2020	8 July 2020	Admin screens functional	Testing Environment	Automation	40	40	40	38	0	2	95.00%	0.00%
15 July 2020	16 July 2020	Release Upgradation test	Testing Environment	Manual	8	8	8	8	0	0	100.00%	0.00%
Release Testing
07/07/2020	07/07/2020	Functional Testing	Test environment	Automation	81	81	81	79	0	2	97.53%	0.00%
07/08/2020	07/08/2020	Regression Testing - Login, Student Attendance, Semester	Test environment	Automation	60	60	60	58	0	2	96.67%	0.00%
08/07/2020	07/08/2020	Regression Testing - CRC, Infrastructure Map & Scatter plot	Test environment	Automation	90	90	90	89	0	1	98.89%	0.00%
14/07/2020	14/07/2020	Load Test	Test environment	JMeter Test	15	15	15	5	0	0
16/07/2020	16/07/2020	Smoke & Sanity Test	Release Environment	Automation	76	76

## Defects
cQube
Project Name	cQube 1.1
Report Name	Defects
Test Type	Manual & Automation
Created By	Devaraja & Chethan
Creation Date	6/12/2020
Reviewed By
Reviewed Date

Defect Id	Functional Area	Defect Description	severity	status	Jira Link
TC_cQube_Nifi_validation_11	Nifi duplicate validation	If the duplicate records containing the same id and same name But containing different lat long details.	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-372
TC_cQube_Nifi_validation_14	Nifi duplicate validation	Check whether count calculation is working properly or not in log file	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-372
16/06/2020
1	School InfraStructure Map Based Report	Click on Schools and check whether each dots on the map / Contains Details, school infrastructure metrics % and other metrics.	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-371
2	School InfraStructure Map Based Report	Click on Gujarath hyper link, Blocks, Clusters and Schools and check / Whether number of schools are equivalent in all the clicks	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-371
3	School InfraStructure Map Based Report	Click on clusters button, Map is not loading / (Only loader is loading)	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-371
17/06/2020
1	School InfraStructure Map Based Report -	Selected cluster's map is not loading / Steps to re-produce: / Goto given below district , block and / cluster , issue that map is not loading / Devbhomi dwarak --> Bhanavad --> Gunda Taluka shala / Amreli --> Khambha --> Trakuda Pri.School / Anand --> Borsad --> Kanbha / Anand --> Khambhat --> Daheda Primary School / Anand --> Khambhat --> Nagra Kumar Shala / Banaskantha --> Amirgadh --> Sarotra / Banaskantha --> Danta --> Sembalpani	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-371
18/06/2020
1	School InfraStructure Scattor plot Report	Goto District select box , district names / are not in orderwise	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
2	School InfraStructure Scattor plot Report	Goto Table , Average % is wrong , % should / be less than 100 but table shows more then / 100%	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
3	School InfraStructure Scattor plot Report	Select district as Jamnagar , select / blocks , No data found issue / Jamnagar --> Jamjodhapur / Jamnagar --> Jamnagar / Jamnagar --> Jodiya / Jamnagar --> Kalavada / Jamnagar --> Lalpura	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
4	School InfraStructure Scattor plot Report	Select district as Porbandar , select / blocks , table data is loading but but no data found / on table / i.e / Porbandhar --> all blocks	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
5	School InfraStructure Scattor plot Report	Select district as Junadhan , select / blocks , table data is not loading but but no data / found on table / i.e / Junadhan -->junadhan	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
6	School InfraStructure Scattor plot Report	Select district as Surendranagar , select / blocks , table data is loading but but no data found / on table / i.e / Surendranagar --> all blocks	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
7	School InfraStructure Scattor plot Report	Select district as Devbhoomi Dwaraka , / choose blocks such as / DevBhomi --> Dwaraka / DevBhomi --> Jamkalyanapur / DevBhomi --> Jamkhambhaliya / table data is loading but no data found on table	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-370
19/06/2020
Tc_cQube_Nifi_Batch_Mode_006	Nifi Batch Processing	Student Attendance template is showing / Data flow error	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-411
Tc_cQube_Nifi_Batch_Mode_007	Nifi Batch Processing	Crc template is showing Stopped componets 2	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-412
Tc_cQube_Nifi_Batch_Mode_008	Nifi Batch Processing	semester template is showing Invalid componets 11	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-413
Tc_cQube_Nifi_Batch_Mode_009	Nifi Batch Processing	static data template is showing Stopped componets 12	Major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-414
20/06/2020
Tc_cQube_CRC_Report_007	CRC Report	Check performance for school wise report download / File is downloading but takes time around 30 sec	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-415
23/06/2020
Tc_cQube_Infrastructure_Report_015	School infrastructure scattor report	Goto donwload report select box , choose school / wise csv and click on download / issue: downloading of school wise csv is taking / more then one minute	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-416
24/06/2020
Tc_cQube_CRC_Report_016	CRC Report	Select district from select box , select block from select box / and select cluster from select box and check with table / data is not loading , shows message as "No data found" / i.e / Valsad/ Vapi/ Vapi / Valsad/ Valsad/ Dived / Valsad/ Valsad/ Dungri / Valsad/ Valsad/ Gorgam / Valsad/ Valsad/ Faldhara / Valsad/ Valsad/ Gorgam / Valsad/ Valsad/ Navera / Valsad/ Umbergaon/ Fansa / Valsad/ Pardi/ Rentlav / Valsad/ Pardi/ Sonwada / Valsad/ Pardi/ Sukhesh / Vadodara/ Padra/ Dabhasa	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-415
30/06/2020
TC_cQube_admin_login_010	Admin login separation	Issue description : / Admin login page only admin can have access but / i have created dashboard report viewer , he also / able to login to admin page	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-417
Grafana
Tc_cQube_Grafana_010	Grafana Dashboard	Emit some data files to the s3 emission bucket / Check whether total files emitted to s3 emission bucket is equivalent to the total files input on the grafana dashboard	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_011	Grafana Dashboard	Emit some data files to the s3 emission bucket / Check whether total files processed in the nifi are equivalent to the data which is showing on the grafana dashboard. / (Total records processed)	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_012	Grafana Dashboard	Emit some data files to the s3 emission bucket. / Check whether total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-418
Tc_cQube_Grafana_013	Grafana Dashboard	Emit some data files to the s3 emission bucket / Check whether total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. / (Total records processed )	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-418
07/07/2020
1	Student Attendance	Choose any district and choose any block, / Block name is showing undefined	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-419
2	Student Attendance	Choose any district and choose any block, / Block names are not showing in the select box	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-419
08/07/2020
Tc_cQube_Admin_Screen_025	Admin screen	Postgres SQL Logs file is / not downloaded	major	Resolved	https://project-sunbird.atlassian.net/browse/CQB-434
09/07/2020
Tc_cQube_Crc_Report_018	CRC report	Selecting some blocks from select box , table is does / not contain records it showing no data found , / click on download button , it start downloading / existing block records not select block record	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-415
TC_cQube_School_Map_060	School infrastructure map report	Goto school infrastructure map report , / check with footer value schools count is 20189, / if click on blocks and school button school count / is same , but different in when click on cluster button	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-433
14/09/2020
Tc_cQube_Regression_Sc_Report_142	School infrastructure scatter plot	Cluster level table data is loaded but there is no data / on table . displayed message as "No data found" / i.e / Dohad Zalod Sarori no data found! / Dohad Sanjeli Limdi no data found!	Minor	Resolved	https://project-sunbird.atlassian.net/browse/CQB-436

## Upgradation to 1.1
Project Name	cQube 1.1
Module Name	Upgrading Of cQube
Test type	Functional testing
Created By	Devaraj
Creation Date	7/13/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Tc_cQube_Upgradability_001	Check wheather following options are displayed or not while installing postgres sql / 1. Skip the Postgres installation (Will backup the data and stores in S3 bucket which mentioned in config.yml file for future reference) / 2. Re-install the Postgres (current database will not be backed-up ) / 3. Exit the installation	1. Skip the Postgres installation (Will backup the data and stores in S3 bucket which mentioned in config.yml file for future reference) / 2. Re-install the Postgres (current database will not be backed-up ) / 3. Exit the installation / Options must be displayed while installing	Same as expected	Pass
Tc_cQube_Upgradability_002	Choose the below option / 1. Skip the Postgres installation (Will backup the data and stores in S3 bucket which mentioned in config.yml file for future reference)	Data must be take backup and stored in the / s3 bucket and installation of postgres sql / must be skip	Same as expected	Pass
Tc_cQube_Upgradability_003	Choose the / 2. Re-install the Postgres (current database will not be backed-up )	New Postgres sql will be installed without / taking the backup	Same as expected	Pass
Tc_cQube_Upgradability_004	Choose the / 3. Exit the installation	Installation must be stopped	Same as expected	Pass
	Check whether the backup database is present in the / postgres sql or not	Backup database must be present in the / postgres sql	Same as expected	Pass
Tc_cQube_Upgradability_006	Check whether New Nifi template is loaded or not	New Nifi template must be loaded	Same as expected	Pass
Tc_cQube_Upgradability_007	Check whether cQube admin login are successfully installed / or not	cQube admin login ui must be opened once / we connected to vpn	Same as expected	Pass
Tc_cQube_Upgradability_008	Check whether cQube login are successfully installed / or not	cQube login must be opened	Same as expected	Pass

## Nifi Duplicate Record Validation Test
cQube 1.1
Project Name	cQube 1.1
Module Name	Nifi duplicate records validation
Test type	Manual
Created By	Devaraj
Creation Date	12 June 2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
TC_cQube_Nifi_validation_01	Check whether data files are loaded into the Nifi process from S3 input bucket	Data files must be loaded form s3 input bucket to nifi process.	same as expected	Pass
TC_cQube_Nifi_validation_02	Check whether nifi read all the records from the data files.	Nifi should read the all the records from data files.	same as expected	Pass
TC_cQube_Nifi_validation_03	Check whether nifi performs the validation or not by writing a grouping query.	Nifi should perform validation.	same as expected	Pass
TC_cQube_Nifi_validation_04	Check the output without duplicates .	Nifi should fetch the files from s3 input bucket and records should be inserted into table.	same as expected	Pass
TC_cQube_Nifi_validation_05	Check whether nifi performs validation on Duplicate records / 1.copy the first two records in the file and paste it below the third / Record.	Nifi should perform validation and duplicate records must be eliminated.	same as expected	Pass
TC_cQube_Nifi_validation_06	Check which duplicate records will nifi eliminate from the file / 1.Manually make some duplicate records as mirror image records.	One record should be considered and rest of the duplicate records should eliminate.	same as expected	Pass
TC_cQube_Nifi_validation_07	Check whether nifi eliminate same id with different values in the file.	Nifi should eliminate both the records.	same as expected	Pass
TC_cQube_Nifi_validation_08	Check whether nifi processes the records which are having the same id, / Same name and different values. / - Check the destination table containing id as a primary key	Nifi should eliminate both the records.	same as expected	Pass
TC_cQube_Nifi_validation_09	Check whether Nifi performs blank line validation and store the blank lines count in the log_summnary table	Nifi should performs blank line validation and store the blank lines count in the log_summnary table	same as expected	Pass
TC_cQube_Nifi_validation_10	Check whether nifi processes the records which are having the different id, / Same name and same values.	Nifi should process and records should be inserted into table.	same as expected	Pass
TC_cQube_Nifi_validation_11	Geo metric Duplication check -district, block, cluster and schools. / If the duplicate records containing the same id and same name / But containing different lat long details.	Nifi should elimiate both the records.	same as expected	Pass
TC_cQube_Nifi_validation_12	Check whether nifi removes the records, where the records having null id's	Nifi should eliminate the those records.	same as expected	Pass
TC_cQube_Nifi_validation_13	Check whether duplicate records are stored in the logs file.	Duplicate records should be stored in the log file.	same as expected	Pass
TC_cQube_Nifi_validation_14	Check whether count calculation is working properly or not in log file	Count should match	same as expected	Pass

## Nifi Process Grouping
cQube 1.1
Project Name	cQube 1.1
Module Name	Nifi Batch Processing
Test type	Manual
Created By	Devaraj
Creation Date	17 June 2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Tc_cQube_Nifi_Batch_Mode_001	Check whether nifi successfully installed or not by ansible script	Niifi should be successfully installed and started	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_002	Check whether Student Attendance template is successfully loaded or not / While installing	Student attendance template must be loaded by ansible script while installing	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_003	Check whether Crc template is successfully loaded or not While installing	Crc template must be loaded / by ansible script while installing	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_004	Check whether semester template is successfully loaded or not While installing	Semester template must be loaded / by ansible script while installing	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_005	Check whether static data template is successfully loaded or not While installing	Static data template must be loaded / by ansible script while installing	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_006	Check whether Student Attendance template is instantiated successfully and / configured or not	Running Components should not be 0 / ie Play Button(ex: 39), / Stopped Components should be 0 / ie.Square Button(ex:0), / Invalid componenets should be 0 / Ie .Triangle Button(ex:0)	Data flow error	Pass
Tc_cQube_Nifi_Batch_Mode_007	Check whether Crc template is instantiated successfully and / configured or not	Running Components should not be 0 / ie Play Button(ex: 39), / Stopped Components should be 0 / ie.Square Button(ex:0), / Invalid componenets should be 0 / Ie .Triangle Button(ex:0)	Instatiated But showing / Stopped componets 2	Pass
Tc_cQube_Nifi_Batch_Mode_008	Check whether semester template is instantiated successfully and / configured or not	Running Components should not be 0 / ie Play Button(ex: 39), / Stopped Components should be 0 / ie.Square Button(ex:0), / Invalid componenets should be 0 / Ie .Triangle Button(ex:0)	Instatiated But showing / Invalid componets 11	Pass
Tc_cQube_Nifi_Batch_Mode_009	Check whether static data template is instantiated successfully and / configured or not	Running Components should not be 0 / ie Play Button(ex: 39), / Stopped Components should be 0 / ie.Square Button(ex:0), / Invalid componenets should be 0 / Ie .Triangle Button(ex:0)	Instatiated But showing / Stopped componets 12	Pass
Tc_cQube_Nifi_Batch_Mode_010	Check whether Student Attendance template is able to disable and stop the / Processor Manually	Student Attendance template must be stopped	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_011	Check whether Crc template is able to disable and stop the / Processor Manually	Crc template must be stopped	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_012	Check whether Semester is able to disable and stop the / Processor Manually	Semester template must be stopped	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_013	Check whether Static data template is able to disable and stop the / Processor Manually	Static data template must be stopped	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_014	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Click on Menu bar / 3.Navigate to templates / 4.Check whether student attendance, crc, semester and static data template / Names are displayed or not	student attendance, crc, semester and static data template name should be displayed in the Nifi template section	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_015	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student attendance transformer / 3.Right click on student_attendance_processor / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_016	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student attendance transformer / 3.Right click on student_attendance_processor / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_017	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on crc processor / 3.Right click on crc_processor / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_018	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on crc processor / 3.Right click on crc_processor / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_019	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student semester transformer / 3.Right click on student_semester_processor / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_020	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student semester transformer / 3.Right click on student_semester_processor / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_021	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on static data transformer / 3.Right click on static_data_processor / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_022	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on static_data_ transformer / 3.Right click on static_data_processor / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_023	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student attendance transformer / 3.Right click on cQube_raw_data_fetch_attendance Configuration / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_024	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student attendance transformer / 3.Right click on cQube_raw_data_fetch_attendance Configuration / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_025	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on crc processor / 3.Right click on cQube_raw_data_fetch_crc Configuration / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_026	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on crc processor / 3.Right click on cQube_raw_data_fetch_crc Configuration / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_027	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student semester transformer / 3.Right click on student_assessment_processor Configuration / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_028	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on student semester transformer / 3.Right click on student_assessment_processor Configuration / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_029	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on static data transformer / 3.Right click on cQube_raw_data_fetch_static Configuration / 4. Goto configure / 4.Check Process Group Name and Process Group Parameter Context are / Configured or not	Process Group Name and Process Group Parameter Context must be configured	Same as Expected	Pass
Tc_cQube_Nifi_Batch_Mode_030	1.Enter url <http://<ip>:8096/nifi> on the search bar / 2.Double click on static_data_ transformer / 3.Right click on cQube_raw_data_fetch_static Configuration / 4. Goto configure / 4.Check whether all the controller-services are enabled or not	All the Controller -services must be enabled	Same as Expected	Pass

## Grafanna
Project Name	cQube 1.1
Module Name	Grafanna_Dashboard
Test type	Manual
Created By	Devaraja
Creation Date	6/30/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Input data	Expected Result	Actual Result	Status
Tc_cQube_Grafana_001	Check whether login page of grafana is displayed or not / 1.Enter <ip:9000>	http://<ip>:9000/	Grafana login page must be displayed	Same as expected	Pass
Tc_cQube_Grafana_002	Check whether home page of grafana is displayed or not / 1.Enter <ip:9000> / 2.Enter valid username and password / 3.Click on login	username: / password:	Grafana home page must be displayed	Same as expected	Pass
Tc_cQube_Grafana_003	Check whether cQube monitoring dashboard is displayed or not	http://<ip>:9000/ username: password:	cQube monitoring dashboard must be displayed	Same as expected	Pass
Tc_cQube_Grafana_004	Check whether cpu utilization,memory usage,server-storage current,Nifi jvm heap memory used,Nifi-jvm heap usage,Total files and Total records graphs are displayed or not		Server-storage current,Nifi jvm heap memory used,Nifi-jvm heap usage, Total files nad Total records graphs must be displayed	Same as expected	Pass
Tc_cQube_Grafana_005	Check whether cpu utilization (in percentage % ) of graph / in the grafana is displaying proper data or not		Cpu utilization in the server is equaivalent / to the data which is displaying on the / grafana dashboard	Same as expected	Pass
Tc_cQube_Grafana_006	Check whether memory usage (in percentage % ) of graph / in the grafana is displaying proper data or not		Memory usage in the server is equaivalent / to the data which is displaying on the / grafana dashboard	Same as expected	Pass
Tc_cQube_Grafana_007	Check whether sever-storage current(in %) of graph in the grafana is displaying proper data or not		Server storage in the server is equaivalent / to the data which is displaying on the / grafana dashboard	Same as expected	Pass
Tc_cQube_Grafana_008	Check whether Nifi-jvm heap memory usage is displaying proper data or not		Nifi-jvm heap memory usage in the server is equaivalent to the data which is displaying on the grafana dashboard	Same as expected	Pass
Tc_cQube_Grafana_009	Check whether Nifi-jvm heap memory usage(in percentage %) is displaying proper data or not		Nifi-jvm heap memory usage in the server is equaivalent to the data which is displaying on the grafana dashboard	Same as expected	Pass
Tc_cQube_Grafana_010	Emit some data files to the s3 emission bucket / Check whether total files emitted to s3 emission bucket is equivalent to the total files input on the grafana dashboard		Total files emitted to s3 emission bucket must be equivalent to the Total files input on the grafana dashboard	No Data showing / on the grafana dashboard	Pass
Tc_cQube_Grafana_011	Emit some data files to the s3 emission bucket / Check whether total files processed in the nifi are equivalent to the data which is showing on the grafana dashboard. / (Total records processed)		Total files processed in the nifi must be equivalent to the data which is showing on the grafana dashboard. / (Total records processed)	No Data showing / on the grafana dashboard	Pass
Tc_cQube_Grafana_012	Emit some data files to the s3 emission bucket. / Check whether total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard		Total records emitted to the s3 emission bucket is equivalent to the total records input on the grafana dashboard	No Data showing / on the grafana dashboard	Pass
Tc_cQube_Grafana_013	Emit some data files to the s3 emission bucket / Check whether total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. / (Total records processed )		Total records processed in the nifi are equivalent to the data which is showing on the grafana dashboard. / (Total records processed )	No Data showing / on the grafana dashboard	Pass
Tc_cQube_Grafana_014	Check the total files section of grafana dashboard / without emitting the data to the s3 emission bucket		No data must be displayed	Same as expected	Pass
Tc_cQube_Grafana_015	Check the total records section of grafana dashboard / without emitting the data to the s3 emission bucket		No data must be displayed	Same as expected	Pass

## Load Testing
Project Name	cQube 1.1
Module Name	Load Testing
Test type	JMeter test
Created By	Devaraja
Creation Date	7/9/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Number Of Users	Status	Average Total Min Response Time	Average Total Max Response Time
Tc_cQube_Load_001	1.Login to cQube application. / 2.Navigate to student attendance report. / 3.Click on schools / 4.Check the respose time with different users	300	Fail	1sec	73.749sec
		270	Fail	2.14sec	74.241sec
		250	Pass	3.0sec	65.889sec

Tc_cQube_Load_002	1.Login to cQube application. / 2.Navigate to Crc report. / 3.Click on schools / 4.Check the respose time with different users	200	Fail	3.8sec	102.0sec
		150	Fail	2.154sec	89.296sec
		100	Pass	1.2sec	66.00sec

Tc_cQube_Load_003	1.Login to cQube application. / 2.Navigate to semester. / 3.Click on schools / 4.Check the respose time with different users	200	Fail	2.632sec	77.422sec
		170	Fail	3.7sec	64.018sec
		100	Pass	1.6sec	39.15sec

Tc_cQube_Load_004	1.Login to cQube application. / 2.Navigate to school infrastructure map report. / 3.Click on schools / 4.Check the respose time with different users	300	Fail	2.2sec	108.255sec
		250	Fail	0.8sec	92.381sec
		200	Pass	1.1sec	86.448sec

Tc_cQube_Load_005	1.Login to cQube application. / 2.Navigate to school infrastructure report. / 3.Click on schools / 4.Check the respose time with different users	200	Fail	0.6sec	123.248sec
		150	Fail	1.2sec	94.716sec
		100	Pass	0.941sec	77.842sec

## Admin_Screen
cQube
Project Name	cQube 1.1
Module Name	Admin_Screen
Test Type	Automation
Created By	Chetan & Devaraja
Creation Date	07/08/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Test Data	Expected Result	Actual Result	Status
Automation Testcases
Tc_cQube_Admin_Screen_001	Check weather admin login page is displayed or not through vpn based port		Admin login should be display	Same as expected	Pass
Tc_cQube_Admin_Screen_002	Check weather admin is login through / admin login page	Valid email & / Valid password	Admin should be login to admin / user page	Same as expected	Pass
Tc_cQube_Admin_Screen_003	Login to admin user , check weather only create / user and chage password options are present or not		Create user and change password should be display in screen	Same as expected	Pass
Tc_cQube_Admin_Screen_004	Check weather admin is able to / create new user or not		New user is create and green message should be display	Same as expected	Pass
Tc_cQube_Admin_Screen_005	Check weather change password is working or not	Enter new password and / Enter conf password	Password should be change	Same as expected	Pass
Tc_cQube_Admin_Screen_006	Login to admin page again , check / new password is working or not	Valid email & new password	Login to admin page	Same as expected	Pass
Tc_cQube_Admin_Screen_007	Create admin role		Admin role to be should created	Same as expected	Pass
Tc_cQube_Admin_Screen_008	Create dashboard report viewer		Dashboard report viewer should be create	Same as expected	Pass
Tc_cQube_Admin_Screen_009	Check newly created admin user in vpn based		Admin should be logined and create user and change password should be present	Same as expected	Pass
Tc_cQube_Admin_Screen_010	Check newly created dashboard report viewer is should not login to vpn based		Vpn based admin login should be not allow to dashboard report viewer to login	Same as expected	Pass
Tc_cQube_Admin_Screen_011	Check newly created dashboard report viewer / is logined to cqube application and check in dashboard contains change password button is present or not		Dashboard report viewer should be logined to cqube application	Same as expected	Pass
Tc_cQube_Admin_Screen_012	Goto logs , choose log type as Application and / select log name as node info logs and check / wether file is downloading or not		Node info log csv file should be / download	Same as expected	Pass
Tc_cQube_Admin_Screen_013	Goto logs , choose log type as Application and / select log name as node error logs and check / wether file is downloading or not		Node info error csv file should be / download	Same as expected	Pass
Tc_cQube_Admin_Screen_014	Goto logs , choose log type as Application and / select log name as angular info logs and check / wether file is downloading or not		Angular info log should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_015	Goto logs , choose log type as Application and / select log name as angular error logs and check / wether file is downloading or not		Angular error log should be / download	Same as expected	Pass
Tc_cQube_Admin_Screen_016	Goto logs , choose log type as Admin and / select log name as node info logs and check / wether file is downloading or not		Node info log csv file should / be download	Same as expected	Pass
Tc_cQube_Admin_Screen_017	Goto logs , choose log type as admin and / select log name as node error logs and check / wether file is downloading or not		Node info error csv file should be / download	Same as expected	Pass
Tc_cQube_Admin_Screen_018	Goto logs , choose log type as admin and / select log name as angular info logs and check / wether file is downloading or not		Angular info log should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_019	Goto logs , choose log type as admin and / select log name as angular error logs and check / wether file is downloading or not		Angular error log should be / download	Same as expected	Pass
Tc_cQube_Admin_Screen_020	Goto logs , choose log type as nifi and / select log name as app logs and check / wether file is downloading or not		App logs file should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_021	Goto logs , choose log type as nifi and / select log name as Bootstrap logs and check / wether file is downloading or not		Bootstrap logs should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_022	Goto logs , choose log type as python and / select log name as access logs and check / wether file is downloading or not		Access log should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_023	Goto logs , choose log type as python and / select log name as error logs and check / wether file is downloading or not		Error logs should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_024	Goto logs , choose log type as System and / select log name as system logs and check / wether file is downloading or not		System logs should be download	Same as expected	Pass
Tc_cQube_Admin_Screen_025	Goto logs , choose log type as postgres and / select log name as postgress and check / wether file is downloading or not		Postgress sql logs should be / download	Postgres SQL Logs file is / not downloaded	Pass
Tc_cQube_Admin_Screen_026	Goto Dashboard of cQube dashboard , click / on all Users and check weather navigated to / all users page or not		User's list should be display	Same as expected	Pass
Tc_cQube_Admin_Screen_027	Goto user list page , click on table swap icons / and check ascending or descending orderwise / is working or not		Table should be change order once / click on table swap icons	Same as expected	Pass
Tc_cQube_Admin_Screen_028	Goto userlist page , click on Activated button , / check weather working or not		Activate button should show pop / box once click on it	Same as expected	Pass
Tc_cQube_Admin_Screen_029	Goto userlist page , click on newly created user / Activated button , and click ok on deactivate pop / notification and check status is changed or not		Status should be change	Status should not / changing	Pass
Tc_cQube_Admin_Screen_030	Goto userlist page , click on Deactivate button , / and click ok on activate pop notification and / check status is changed or not		Status should be change	Same as expected	Pass
Tc_cQube_Admin_Screen_031	Goto userlist table check with name data , it / shoud not contain null in there in name		Names should not be contains / name with null	Same as expected	Pass
Tc_cQube_Admin_Screen_032	Goto cQube dashboard , click on S3 file / download and check weather working or not		S3 files download page should be / display	Same as expected	Pass
Tc_cQube_Admin_Screen_033	Goto S3 file download page , check weather / select drop down options are selectble or not		Select dropdown options should / be selectable	Same as expected	Pass
Tc_cQube_Admin_Screen_034	Goto S3 file download page ,select each / dropdown and choose file and click on download / and check weather file downloading or not		Selected file should be downloaded	Same as expected	Pass
Tc_cQube_Admin_Screen_035	Goto admin login landing page, click on all / icons and check weather working or not		All icons should be navigate to there / page	Same as expected	Pass
Tc_cQube_Admin_Screen_036	click on logout button and check weather logout / is working or not		Navigate back to admin login page	Same as expected	Pass
Tc_cQube_Admin_Screen_037	Goto admin login page ,click on each dashboard / icons		Dashboard icons should be clickable	Same as expected	Pass
Tc_cQube_Admin_Screen_038	Create user and check weather creater user is / present in all user list or not		Newly created user should be / present in all user list	Same as expected	Pass
Tc_cQube_Admin_Screen_039	Goto to all users , check with search box is / working or not		Search box should be work	Same as expected	Pass
Tc_cQube_Admin_Screen_040	Click on monitoring details icons , check weather / it is navigated to grafana dashboard or not		Navigated to grafana dashboard / shouldbe display	Same as expected	Pass

## CRC Report
Project Name	cQube 1.1
Module Name	CRC_Performance
Test type	Automation
Created By	Chetan & Devaraj
Creation Date	6/19/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Automation Test Cases
Tc_cQube_Crc_Report_001	Check whether dashboad menu of cqube is working or not	Menu list should be Open	Same as expected	Pass
Tc_cQube_Crc_Report_002	Check whether dashboad menu of / CRC Report is working or not	Crc report for: Gujarat Should display	Same as expected	Pass
Tc_cQube_Crc_Report_003	Check performance of crc report Goto Dashboard / menu , click on crc report and check weather crc / report is loaded within 5 sec or not	Crc report must be loaded in within 5 sec	Same as expected	Pass
Tc_cQube_Crc_Report_004	Check performance for district wise report download	District wise csv should be downloaded within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_005	Check performance for block wise report download	Block wise csv should be downloaded within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_006	Check performance for cluster wise report download	Cluster wise csv should be download within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_007	Check performance for school wise report download	School wise csv should be download within / specified time	School wise csv is / not downloaded at specified / time i.e 20 seconds	Pass
Tc_cQube_Crc_Report_008	Check performance for choose district , choose / block and choose cluster from select box and check / weather table data is loading or not within / specified time	Table data should load within specified time	Same as expected	Pass
Tc_cQube_Crc_Report_009	Download the block wise csv and check / downloading or not	Blockwise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_010	Download the cluster wise csv and check downloading / or not	Cluster wise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_011	Download the school wise csv and check / downloading or not	School wise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_012	Check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
Tc_cQube_Crc_Report_013	Select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_014	Select district from select box ,select block from / select box ,click on download icon check weather / cluster level csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_015	Select district from select box ,select block / from select box ,select cluster from select box click / on download icon check weather school level csv is / downloading or not	School level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_016	Select district from select box , select block from / select box and select cluster from select box and / check with table data is loading or not	School level table data should be display	Some of school data is loading but / not displaying on screen	Pass
Tc_cQube_Crc_Report_017	Select district from select box , select block / from select box and check with table data is / loading or not	Cluster level table data should be display	Cluster level data is not loaded in / some of cluster	Pass
Tc_cQube_Crc_Report_018	Select district from select box , check with table / data is loading or not	Block level table data should be display	Same as expected	Pass
Tc_cQube_Crc_Report_019	Check with logout functionality	Navigate back to login page	Same as expected	Pass
Tc_cQube_Crc_Report_020	Check with x and y axis values are selectable or not	Both x and y axis values should be sele / -ctable	Same as expected	Pass
Tc_cQube_Crc_Report_021	Check with districtwise total no of schools details	District wise no of school value is should be / same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_022	Check with districtwise total no of schools visited	District wise no of school visited value is / should same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_023	Check with districtwise total no of schools visits	District wise no of school visites value is / should same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_024	Click on district name on the table and check / whether ascending and descending functionality is / working or not	District name should be sorted based on the / input	Same as expected	Pass
Tc_cQube_Crc_Report_025	Check hyperlinks are navigating back to the / districtwise crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
Tc_cQube_Crc_Report_026	Select district,block and cluster and click on home icon	Navigated to crc report	Same as expected	Pass
Tc_cQube_Crc_Report_027	Check on crc report and click on logout	Login page should be displayed	Same as expected	Pass

## School Infrastructure Map Report
cQube 1.1
Project Name	cQube 1.1
Module Name	School Infrastructure Map Based Report
Test type	Manual And Automation
Created By	Chetan & Devaraj
Creation Date	6/16/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Manual Test Cases
Tc_cQube_School_Infra_001	Click on gujarath hyper link and check whether each dots on the map / Contains Details, school infrastructure metrics % and other metrics	All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information	Same as expected	Pass
Tc_cQube_School_Infra_002	Click on Blocks and check whether check whether each dots on the map / Contains Details, school infrastructure metrics % and other metrics.	All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information	Same as expected	Pass
Tc_cQube_School_Infra_003	Click on Clusters and check whether check whether each dots on the map / Contains Details, school infrastructure metrics % and other metrics.	All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information	Same as expected	Pass
Tc_cQube_School_Infra_004	Click on Schools and check whether check whether each dots on the map / Contains Details, school infrastructure metrics % and other metrics.	All the markers present on the map should contains Details, school infrastructure metrics % and other metrics information	Same as expected	Pass
Tc_cQube_School_Infra_005	Select school_infra from select box and check whether infrastructure_score is / Highligted on the markers	Infrastructure_score should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_006	Select boy’s toilet from select box and check whether infrastructure_score is / Highligted on the markers	Boy’s toilet should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_007	Select drinking water from select box and check whether infrastructure_score is / Highligted on the markers	Drinking water should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_008	Select electricity from select box and check whether infrastructure_score is / Highligted on the markers	Electricity should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_009	Select girl’s toilet from select box and check whether infrastructure_score is / Highligted on the markers	Girl’s toilet should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_010	Select hand pump’s from select box and check whether infrastructure_score is / Highligted on the markers	Hand pump’s should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_011	Select hand wash from select box and check whether infrastructure_score is / Highligted on the markers	Hand wash should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_012	Select library from select box and check whether infrastructure_score is / Highligted on the markers	Library should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_013	Select solar panel from select box and check whether infrastructure_score is / Highligted on the markers	Solar panel should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_014	Select tap water from select box and check whether infrastructure_score is / Highligted on the markers	Tap water should be highlighted on the markers	Same as expected	Pass
Tc_cQube_School_Infra_015	Select toilet’s from select box and check whether infrastructure_score is / Highligted on the markers	Toilet’s should be highlighted on the markers	Same as expected	Pass
Automation Test Cases
Tc_cQube_School_Infra_016	Check whether dashboad menu of cqube is working or not	Dashboard menu list to be display	Same as expected	Pass
Tc_cQube_School_Infra_017	Check whether dashboad menu of School infrastructure is working or not	Navigate to School infrastructure Report	Same as expected	Pass
Tc_cQube_School_Infra_018	Click on School infrastructure options , check weather options displayed or not	options should be display	Same as expected	Pass
Tc_cQube_School_Infra_019	Goto Dashboard , click on school infrastructure , and click on Report(map) , / Check weather is navigate to Report(map) or not	Navigate to Report(map) page should be display	Same as expected	Pass
Tc_cQube_School_Infra_020	Check whether map is displayed or not / On the school infra map based Report	Map should be display	Same as expected	Pass
Tc_cQube_School_Infra_021	Check whether Points are displayed or not / On the map	Points should be displayed on the map	Same as expected	Pass
Tc_cQube_School_Infra_022	Click on Gujarat hyper link	It should be refresh school infrastructure page	Same as expected	Pass
Tc_cQube_School_Infra_023	Click on Download icon and check weather csv file is downloading or not	Csv file is should be download once click on / Download_icon	Same as expected	Pass
Tc_cQube_School_Infra_024	Click on District select box and check weather select box contains options or / Not	District select box should be display list of districts	Same as expected	Pass
Tc_cQube_School_Infra_025	Select any District from select box , and check weather choosed district is / selected Or not	District record should be display of selected district	Same as expected	Pass
Tc_cQube_School_Infra_026	Select any District from select box ,select any block from select box and check / Weather block is selected or not	block record should be display of selected block	Same as expected	Pass
Tc_cQube_School_Infra_027	Select any District from select box ,select any block from select box and choose / Any cluster name from select box	Cluster record should be display of selected cluster	Same as expected	Pass
Tc_cQube_School_Infra_028	Select any district from select box and click on download button to check it is / Downloading or not	Download the selected districtwise csv file	Same as expected	Pass
Tc_cQube_School_Infra_029	Select any district from select box and select any block from select box / click on donwload button to check weather its downloading or not	Download the selected Blockwise csv file	Same as expected	Pass
Tc_cQube_School_Infra_030	Select any district from select box and select any block from select box and / Select Cluster from select box ,click on donwload button to check weather it is / Downloading or not	Download the selected Clusterwise csv file	Same as expected	Pass
Tc_cQube_School_Infra_031	Select any district from select box and click on Home icon check weather page / is Navigated to school_infrastructure page or not	Navigate back to school infrastructure home page	Same as expected	Pass
Tc_cQube_School_Infra_032	Click on logout button	Navigate back to login page of cQube application	Same as expected	Pass
Tc_cQube_School_Infra_033	Click on Catories select box , check weather cataory list is displaying or not	List of catagories to be display	Same as expected	Pass
Tc_cQube_School_Infra_034	select any option from Infra_scores select box , check in map tooltip should / contains Selected option record	It should be display selected option record on tool tip of map	Same as expected	Pass
Tc_cQube_School_Infra_035	Goto Infra_scores drop down and select as Infra_score	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_036	Goto Infra_scores drop down and select as Handwash_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_037	Goto Infra_scores drop down and select as Solar_panel_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_038	Goto Infra_scores drop down and select as Library_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_039	Goto Infra_scores drop down and select as Drinking_Water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_040	Goto Infra_scores drop down and select as Tap_water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_041	Goto Infra_scores drop down and select as Hand_Pumps_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_042	Goto Infra_scores drop down and select as Electricity_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_043	Goto Infra_scores drop down and select as Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_044	Goto Infra_scores drop down and select as Boy’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_045	Goto Infra_scores drop down and select as Girl’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
Tc_cQube_School_Infra_046	Click on Blocks button , check weather block level map is displaying or not	Block level records should be display on map	Same as expected	Pass
Tc_cQube_School_Infra_047	Click on Blocks button , check with footer informations	Block level footer information to be display	Same as expected	Pass
Tc_cQube_School_Infra_048	Click on Blocks button , and click on download button	block level csv should be download	Same as expected	Pass
Tc_cQube_School_Infra_049	Click on Clusters button , check weather block level map is displaying or not	Cluster level records should be display on map	Same as expected	Pass
Tc_cQube_School_Infra_050	Click on Cluster button , check with footer informations	Cluster level footer information to be display	Same as expected	Pass
Tc_cQube_School_Infra_051	Click on Clusters button , and click on download button	Cluster level csv should be download	Same as expected	Pass
Tc_cQube_School_Infra_052	Click on Schools button , check weather block level map is displaying or not	School level records should be display on map	Same as expected	Pass
Tc_cQube_School_Infra_053	Click on Schools button , and click on download button	School level footer information to be display	Same as expected	Pass
Tc_cQube_School_Infra_054	Click on Schools button , check with footer informations	School level csv should be download	Same as expected	Pass
Tc_cQube_School_Infra_055	Click on Gujarath hyper link, Blocks, Clusters and Schools and check / Whether number of schools are equivalent in all the clicks" / Number of schools should be equal for / -Blocks / -Clusters / -Schools	Number of schools should be equal for each block , / Cluster and school	Cluster level data mismatched	Pass

## Infrastructure - Scattor Plot
Project Name	cQube 1.1
Module Name	School Infrastructure Report (Scattor plot)
Test type	Automation
Created By	Chetan & Devaraj
Creation Date	6/18/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Automation Test Cases
Tc_cQube_Infrastructure_Report_001	Check whether dashboad menu of cqube is working or not	Menu list should be Open	same as expected	Pass
Tc_cQube_Infrastructure_Report_002	Check whether dashboad menu of / School infrastructure report is working or not	School Infrastructure report for: Gujarat Should display	same as expected	Pass
Tc_cQube_Infrastructure_Report_003	Check page contains Graph and Tables	Graph and table should be display	same as expected	Pass
Tc_cQube_Infrastructure_Report_004	Select districtwise csv option from download report / from select box and click on donwload icon	It should download the selected / download report csv	Same as expected	Pass
Tc_cQube_Infrastructure_Report_005	Select blockwise csv option from download report / from select box and click on donwload icon	It should download the selected / download report csv	Same as expected	Pass
Tc_cQube_Infrastructure_Report_006	Select clusterwise csv option from download report / from select box and click on donwload icon	It should download the selected / download report csv	Same as expected	Pass
Tc_cQube_Infrastructure_Report_007	Select schoolwise csv option from download report / from select box and click on donwload icon	It should download the selected / download report csv	Same as expected	Pass
Tc_cQube_Infrastructure_Report_008	Check hyperlinks are navigating back to the districtwise / crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
Tc_cQube_Infrastructure_Report_009	Check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
Tc_cQube_Infrastructure_Report_010	Select district,block and click on home icon	Navigated to crc report	Same as expected	Pass
Tc_cQube_Infrastructure_Report_011	Select district,block and cluster and click on home icon	Navigated to crc report	Same as expected	Pass
Tc_cQube_Infrastructure_Report_012	Click on district name on the table and check whether / ascending and descending functionality is working or not	District name should be sorted based on the / input	Same as expected	Pass
Tc_cQube_Infrastructure_Report_013	Select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
Tc_cQube_Infrastructure_Report_014	Select district from select box ,select block from select / box ,click on download icon check weather cluster level / csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
Tc_cQube_Infrastructure_Report_015	Select district from select box ,select block from select / box ,select cluster from select box click on download / -icon check weather school level csv is downloading or not	School level csv should be download	Some of School level data is / showing no data found	Pass
Tc_cQube_Infrastructure_Report_016	Select district from select box , select block from select box / and select cluster from select box and check with table / data is loading or not	School level table data should be display	Some of School table data is / showing no data found	Pass
Tc_cQube_Infrastructure_Report_017	Select district from select box , select block from select box / and check with table data is loading or not	Cluster level table data should be display	Some of cluster level table data is / showing no data found	Pass
Tc_cQube_Infrastructure_Report_018	Select district from select box , check with table data is / loading or not	Block level table data should be display	Same as expected	Pass
Tc_cQube_Infrastructure_Report_019	Goto district wise table data and check with metric / percentages	Average metrics percentage should be / below or equal 100%	Average contains more then 100% / in district wise table data	Pass
Tc_cQube_Infrastructure_Report_020	Goto District wise select box and check weather / district names are in order wise or not	District names should be in orderwise	District names are not in orderwise	Pass
Tc_cQube_Infrastructure_Report_021	Check with x and y axis values are selectable or not	Both x and y axis values should be sele / -ctable	Same as expected	Pass
Tc_cQube_Infrastructure_Report_022	Click on crc report and click on logout	Login page should be displayed	Same as expected	Pass
Tc_cQube_Infrastructure_Report_023	Goto xaxis select box and check options are present / or not	Xaxis options should be display	Same as expected	Pass
Tc_cQube_Infrastructure_Report_024	Goto yaxis select box and check options are present / or not	Yaxis options should be display	Same as expected	Pass

## Functional_Testcases
Project Name	cQube 1.1
Test Case Name	Functional_Testcases
Created By	Chetan & Devaraj
Creation Date	7/7/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Automation Testcases
CRC Report
Tc_cQube_Crc_Report_001	Check whether dashboad menu of cqube is working or not	Menu list should be Open	Same as expected	Pass
Tc_cQube_Crc_Report_002	Check whether dashboad menu of / CRC Report is working or not	CRC report for: Gujarat Should display	Same as expected	Pass
Tc_cQube_Crc_Report_003	Check performance of crc report / Goto Dashboard menu , click on crc report and check / weather crc report is loaded within 5 sec or not	Crc report must be loaded in within 5 sec	Same as expected	Pass
Tc_cQube_Crc_Report_004	Check performance for district wise report download	District wise csv should be downloaded within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_005	Check performance for block wise report download	Block wise csv should be downloaded within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_006	Check performance for cluster wise report download	Cluster wise csv should be download within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_007	Check performance for school wise report download	School wise csv should be download within / specified time	Same as expected	Pass
Tc_cQube_Crc_Report_008	Check performance for choose district , choose block and / choose cluster from select box and check weather table data / is loading or not within specified time	Table data should load within specified time	Same as expected	Pass
Tc_cQube_Crc_Report_009	Download the block wise csv and check downloading / or not	Blockwise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_010	Download the cluster wise csv and check downloading / or not	Cluster wise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_011	Download the school wise csv and check downloading / or not	School wise csv is should be download	Same as expected	Pass
Tc_cQube_Crc_Report_012	Check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
Tc_cQube_Crc_Report_013	Select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_014	Select district from select box ,select block from select / box ,click on download icon check weather cluster level / csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_015	Select district from select box ,select block from select / box ,select cluster from select box click on download / -icon check weather school level csv is downloading or not	School level csv should be download	Same as expected	Pass
Tc_cQube_Crc_Report_016	Select district from select box , select block from select box / and select cluster from select box and check with table / data is loading or not	School level table data should be display	Same as expected	Pass
Tc_cQube_Crc_Report_017	Select district from select box , select block from select box / and check with table data is loading or not	Cluster level table data should be display	Same as expected	Pass
Tc_cQube_Crc_Report_018	Select district from select box , check with table data is / loading or not	Block level table data should be display	Same as expected	Pass
Tc_cQube_Crc_Report_019	Check with logout functionality	Navigate back to login page	Same as expected	Pass
Tc_cQube_Crc_Report_020	Check with x and y axis values are selectable or not	Both x and y axis values should be sele / -ctable	Same as expected	Pass
Tc_cQube_Crc_Report_021	Check with districtwise total no of schools details	District wise no of school value is should be / same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_022	Check with districtwise total no of schools visited	District wise no of school visited value is / should same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_023	Check with districtwise total no of schools visits	District wise no of school visites value is / should same as in districtwise downloaded csv	Same as expected	Pass
Tc_cQube_Crc_Report_024	Click on district name on the table and check whether / ascending and descending functionality is working or not	District name should be sorted based on the / input	Same as expected	Pass
Tc_cQube_Crc_Report_025	Check hyperlinks are navigating back to the districtwise / crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
Tc_cQube_Crc_Report_027	Click on crc report and click on logout	Login page should be displayed	Same as expected	Pass
School infra Map
TC_cQube_School_Map_028	Check whether dashboad menu of cqube is working or not	Dashboard menu list to be display	Same as expected	Pass
TC_cQube_School_Map_029	Check whether dashboad menu of School infrastructure is working or not	Navigate to School infrastructure Report	Same as expected	Pass
TC_cQube_School_Map_030	Click on School infrastructure options , check weather options displayed or not	Options should be display	Same as expected	Pass
TC_cQube_School_Map_031	Goto Dashboard , click on school infrastructure , and click on Report(map) , / Check weather is navigate to Report(map) or not	Navigate to Report(map) page should be display	Same as expected	Pass
TC_cQube_School_Map_032	Check whether map is displayed or not / On the Semester Report	Map should be display	Same as expected	Pass
TC_cQube_School_Map_033	Check whether Points are displayed or not / On the map	Points should be displayed on the map	Same as expected	Pass
TC_cQube_School_Map_034	Click on Gujarat hyper link	It should be refresh school infrastructure page	Same as expected	Pass
TC_cQube_School_Map_035	Click on Download icon and check weather csv file is downloading or not	Csv file is should be download once click on / Download_icon	Same as expected	Pass
TC_cQube_School_Map_036	Click on District select box and check weather select box contains / options or Not	District select box should be display list of districts	Same as expected	Pass
TC_cQube_School_Map_037	Select any district from select box and click on download button to check / it is Downloading or not	Download the selected districtwise csv file	Same as expected	Pass
TC_cQube_School_Map_038	Select any district from select box and select any block from select box / click on donwload button to check weather its downloading or not	Download the selected Blockwise csv file	Same as expected	Pass
TC_cQube_School_Map_039	Select any district from select box and select any block from select box / and Select Cluster from select box ,click on donwload button to check / weather it is Downloading or not	Download the selected Clusterwise csv file	Same as expected	Pass
TC_cQube_School_Map_040	Select any district from select box and click on Home icon check / weather page is Navigated to school_infrastructure page or not	Navigate back to school infrastructure home page	Same as expected	Pass
TC_cQube_School_Map_041	Click on logout button	Navigate back to login page of cQube application	Same as expected	Pass
TC_cQube_School_Map_042	Click on Catories select box , check weather cataory list is displaying or not	List of catagories to be display	Same as expected	Pass
TC_cQube_School_Map_043	Select any option from Infra_scores select box , check in map tooltip should / contains Selected option record	It should be display selected option record on tool tip of map	Same as expected	Pass
TC_cQube_School_Map_044	Goto Infra_scores drop down and select as Infra_score	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_045	Goto Infra_scores drop down and select as Handwash_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_046	Goto Infra_scores drop down and select as Solar_panel_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_047	Goto Infra_scores drop down and select as Library_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_048	Goto Infra_scores drop down and select as Drinking_Water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_049	Goto Infra_scores drop down and select as Tap_water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_050	Goto Infra_scores drop down and select as Hand_Pumps_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_051	Goto Infra_scores drop down and select as Electricity_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_052	Goto Infra_scores drop down and select as Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_053	Goto Infra_scores drop down and select as Boy’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_054	Goto Infra_scores drop down and select as Girl’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
TC_cQube_School_Map_055	Click on Blocks button , check weather block level map is displaying or not	Block level records should be display on map	Same as expected	Pass
TC_cQube_School_Map_056	Click on Blocks button , check with footer informations	Block level footer information to be display	Same as expected	Pass
TC_cQube_School_Map_057	Click on Cluster button , check with footer informations	Cluster level footer information to be display	Same as expected	Pass
TC_cQube_School_Map_058	Click on Clusters button , and click on download button	Cluster level csv should be download	Same as expected	Pass
TC_cQube_School_Map_059	Click on Schools button , check weather block level map is displaying or not	School level records should be display on map	Same as expected	Pass
TC_cQube_School_Map_060	Click on Gujarath hyper link, Blocks, Clusters and Schools and check / Whether number of schools are equivalent in all the clicks" / Number of schools should be equal for / -Blocks / -Clusters / -Schools	Number of schools should be equal for each block , / Cluster and school	Cluster level no of school count / is different from blocks and schools	Resolved
School infra Report
Tc_cQube_School_Report_061	Check whether dashboad menu of cqube is working or not	Menu list should be Open	Same as expected	Pass
Tc_cQube_School_Report_062	Check whether dashboad menu of / School infrastructure report is working or not	School Infrastructure report for: Gujarat Should display	Same as expected	Pass
Tc_cQube_School_Report_063	Check page contains Graph and Tables	Graph and table should be display	Same as expected	Pass
Tc_cQube_School_Report_064	Select districtwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
Tc_cQube_School_Report_065	Select blockwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
Tc_cQube_School_Report_066	Select clusterwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
Tc_cQube_School_Report_067	Select schoolwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
Tc_cQube_School_Report_068	Check hyperlinks are navigating back to the districtwise / crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
Tc_cQube_School_Report_069	Check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
Tc_cQube_School_Report_070	Select district,block and click on home icon	Navigated to crc report	Same as expected	Pass
Tc_cQube_School_Report_071	Select district,block and cluster and click on home icon	Navigated to crc report	Same as expected	Pass
Tc_cQube_School_Report_072	Click on district name on the table and check whether / ascending and descending functionality is working or not	District name should be sorted based on the / input	Same as expected	Pass
Tc_cQube_School_Report_073	Select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
Tc_cQube_School_Report_074	Select district from select box ,select block from select / box ,click on download icon check weather cluster level / csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
Tc_cQube_School_Report_075	Select district from select box ,select block from select / box ,select cluster from select box click on download / -icon check weather school level csv is downloading or not	School level csv should be download	Same as expected	Pass
Tc_cQube_School_Report_076	Select district from select box , select block from select box / and check with table data is loading or not	Cluster level table data should be display	Same as expected	Pass
Tc_cQube_School_Report_077	Select district from select box , check with table data is / loading or not	Block level table data should be display	Same as expected	Pass
Tc_cQube_School_Report_078	Goto District wise select box and check weather / district names are in order wise or not	District names should be in orderwise	Same as expected	Pass
Tc_cQube_School_Report_079	Click on crc report and click on logout	Login page should be displayed	Same as expected	Pass
Tc_cQube_School_Report_080	Goto xaxis select box and check options are present / or not	Xaxis options should be display	Same as expected	Pass
Tc_cQube_School_Report_081	Goto yaxis select box and check options are present / or not	Yaxis options should be display	Same as expected	Pass

## Regression_Testcases
Project Name	cQube 1.1
Test Case Name	Regression_Testcases
Created By	Chetan & Devaraj
Creation Date	7/10/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Automation Testcases
Login
cQube_Regression_Login_001	Login to cQube application with / valid user name and valid password	Navigate to cQube landing page	Same as expected	Pass
cQube_Regression_Login_002	Check login with invalid email id without / password and click on login button	Error message should be display / this is field required	Same as expected	Pass
cQube_Regression_Login_003	Check login with invalid email id with / invalid password and click on login button	Error message should be display / user not found	Same as expected	Pass
cQube_Regression_Login_004	Check with invalid password range below / 4 character and click login button	User able see error message on / screen as minimum 4 character for / password field	Same as expected	Pass
cQube_Regression_Login_005	Check with login without giving credentials	User able see error message on / screen as this field is required	Same as expected	Pass
cQube_Regression_Login_006	Go to login of cQube application , give / valid email and invalid password and check / with login button	User able see error message on / screen	Same as expected	Pass
cQube_Regression_Login_007	Go to login of cQube application , give / invalid email and valid password and check / with login button	User able see error message on / screen	Same as expected	Pass
cQube_Regression_Login_008	Login to cQube application with / valid user name and valid password and / click on logout button	Navigate back to login page	Same as expected	Pass
cQube_Regression_Login_009	Login with valid email and valid passwords / which validity of user expired	User unable to login to application , / error message is should be display / as validity of user is exceeded	Same as expected	Pass
cQube_Regression_Login_010	Login with invalid email id without providing / domain name with valid password	User able to see error message on / screen as invalid emai address	Same as expected	Pass
cQube_Regression_Login_011	Check login to application by / email and password must be less than 4 / character	User able see error message on / screen	Same as expected	Pass
cQube_Regression_Login_012	Enter valid email and valid password and / click on login button , check dashboard / options	Dashboard options should be / display	Same as expected	Pass
cQube_Landing Page				Pass
cQube_Regression_Landing_page_013	Login to cQube application , check weather / navigated to landing page or not	After login , landing page should be display	Same as expected	Pass
cQube_Regression_Landing_page_014	Click on student attendance report icon and check / weather navigated to student attendance report or / not	Navigate to student attendance home page	Same as expected	Pass
cQube_Regression_Landing_page_015	Click on crc report icon and check / weather navigated to crc report or / not	Navigate to crc report home page	Same as expected	Pass
cQube_Regression_Landing_page_016	Click on semester report icon and check / weather navigated to semester report or / not	Navigate to semester report home page	Same as expected	Pass
cQube_Regression_Landing_page_017	Click on teacher attendance report icon and check / weather navigated to teacher attendance report or / not	Navigate to teacher attendance coming soon / page	Same as expected	Pass
cQube_Regression_Landing_page_018	Click on school infrastrure map report icon and / check weather navigated to school infrastructure / map report or not	Navigate to school infrastrure map report / home page	Same as expected	Pass
cQube_Regression_Landing_page_019	Click on school infrastrure scattor report icon and / check weather navigated to school infrastructure / scattor report or not	Navigate to school infrastrure scattor report home / page	Same as expected	Pass
Student Attendance report
cQube_Regression_Student_020	Goto Dashboard , Check whether / dashboad menu of cqube is working or not	Side navigation bar should / Opened	Same as expected	Pass
cQube_Regression_Student_021	Goto Dashboard ,Check whether / dashboad menu of Student Attendence / Reports is working or not	Attendance report for gujarat / Should display	Same as expected	Pass
cQube_Regression_Student_022	Check whether Points are displayed or not / On the map	Points should be displayed on the map	Same as expected	Pass
cQube_Regression_Student_023	Check whether,total number of schools are equal or not / by click on blocks,clusters and schools	Total number of schools must be / equal by click on blocks,clusters / and schools	Same as expected	Pass
cQube_Regression_Student_024	Check whether,total number of students are equal or not / by click on blocks,clusters and schools	Total number of students must be / equal by click on blocks,clusters / and schools	Same as expected	Pass
cQube_Regression_Student_025	Check whether Block Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Student_026	Check whether Cluster Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Student_027	Check whether School Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Student_028	Check whether Download Functionality is working or not	User Should able to see the / Downloaded File	Same as expected	Pass
cQube_Regression_Student_029	Check whether Block level csv file is downloading or not	Block level csv file should be download	Same as expected	Pass
cQube_Regression_Student_030	Check whether cluster level csv file is downloading or not	Cluster level csv file should be download	Same as expected	Pass
cQube_Regression_Student_031	Check whether school level csv file is downloading or not	School level csv file should be download	Same as expected	Pass
cQube_Regression_Student_032	Check whether Each District is selectable or not / From select box and also check whether Blocks-per-district-report is generating or not	Blocks-per-district csv file should be generated	Same as expected	Pass
cQube_Regression_Student_033	Check whether Each block is selectable or not / From select box and also check whether Cluster_per_block_report is generating or not	Cluster_per_block_report csv file should be generated	Same as expected	Pass
cQube_Regression_Student_034	Check whether Each cluster is selectable or not / From select box and also check whether School_per_cluster_report is generating or not	School_per_cluster_report csv file should be generated	Same as expected	Pass
cQube_Regression_Student_035	Check whether Navigation Functionality / Is working or not	Navigation should happens / From cluster level to state level	Same as expected	Pass
cQube_Regression_Student_036	Check whether Home button is working or not	Home button should worl	Same as expected	Pass
cQube_Regression_Student_037	Check Date range by selecting year and month	Date range should be change according to selected / year and month	Same as expected	Pass
cQube_Regression_Student_038	Check Dots are present on the map or not by selecting districts,block and clusters	Dots must be present	Same as expected	Pass
cQube_Regression_Student_039	Check whether Logout Functionality / Is working or not	Login Page should be display	Same as expected	Pass
CRC Report
cQube_Regression_Crc_040	Goto Dashboard ,check whether dashboad / menu of cqube is working or not	Menu list should be Open	Same as expected	Pass
cQube_Regression_Crc_041	Goto Dashboard Check whether dashboad / menu of CRC Report is working or not	Crc report for: Gujarat Should display	Same as expected	Pass
cQube_Regression_Crc_042	Goto Dashboard ,check performance of crc / report Goto Dashboard menu , click on crc / report and check weather crc report is / loaded within 5 sec or not	Crc report must be loaded in within 5 sec	Same as expected	Pass
cQube_Regression_Crc_043	Check performance for district wise report download	District wise csv should be downloaded within / specified time	Same as expected	Pass
cQube_Regression_Crc_044	Check performance for block wise report download	Block wise csv should be downloaded within / specified time	Same as expected	Pass
cQube_Regression_Crc_045	Check performance for cluster wise report download	Cluster wise csv should be download within / specified time	Same as expected	Pass
cQube_Regression_Crc_046	Check performance for school wise report download	School wise csv should be download within / specified time	Same as expected	Pass
cQube_Regression_Crc_047	Check performance for choose district , choose block and / choose cluster from select box and check weather table data / is loading or not within specified time	Table data should load within specified time	Same as expected	Pass
cQube_Regression_Crc_048	Download the block wise csv and check downloading / or not	Blockwise csv is should be download	Same as expected	Pass
cQube_Regression_Crc_049	Download the cluster wise csv and check downloading / or not	Cluster wise csv is should be download	Same as expected	Pass
cQube_Regression_Crc_050	Download the school wise csv and check downloading / or not	School wise csv is should be download	Same as expected	Pass
cQube_Regression_Crc_051	Check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
cQube_Regression_Crc_052	Select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
cQube_Regression_Crc_053	Select district from select box ,select block from select / box ,click on download icon check weather cluster level / csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
cQube_Regression_Crc_054	Select district from select box ,select block from select / box ,select cluster from select box click on download / -icon check weather school level csv is downloading or not	School level csv should be download	Same as expected	Pass
cQube_Regression_Crc_055	Select district from select box , select block from select box / and select cluster from select box and check with table / data is loading or not	School level table data should be display	Same as expected	Pass
cQube_Regression_Crc_056	Select district from select box , select block from select box / and check with table data is loading or not	Cluster level table data should be display	Same as expected	Pass
cQube_Regression_Crc_057	Select district from select box , check with table data is / loading or not	Block level table data should be display	Same as expected	Pass
cQube_Regression_Crc_058	Check with logout functionality	Navigate back to login page	Same as expected	Pass
cQube_Regression_Crc_059	Check with x and y axis values are selectable or not	Both x and y axis values should be sele / -ctable	Same as expected	Pass
cQube_Regression_Crc_060	Check with districtwise total no of schools details	District wise no of school value is should be / same as in districtwise downloaded csv	Same as expected	Pass
cQube_Regression_Crc_061	Check with districtwise total no of schools visited	District wise no of school visited value is / should same as in districtwise downloaded csv	Same as expected	Pass
cQube_Regression_Crc_062	Check with districtwise total no of schools visits	District wise no of school visites value is / should same as in districtwise downloaded csv	Same as expected	Pass
cQube_Regression_Crc_063	Click on district name on the table and check whether / ascending and descending functionality is working or not	District name should be sorted based on the / input	Same as expected	Pass
cQube_Regression_Crc_064	Check hyperlinks are navigating back to the districtwise / crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
cQube_Regression_Crc_065	Select district,block and cluster and click on home icon	Navigated to crc report	Same as expected	Pass
cQube_Regression_Crc_066	Click on crc report and click on logout	Login page should be displayed	Same as expected	Pass
Semester Report
cQube_Regression_Semester_067	Check whether dashboad menu of / cqube is working or not	Side navigation bar should / Opened	Same as expected	Pass
cQube_Regression_Semester_068	Check whether dashboad menu of / Student Attendence Reports is working or not	Attendance report for gujarat / Should display	Same as expected	Pass
cQube_Regression_Semester_069	Check whether Points are displayed or not / On the map	Points should be displayed on the map	Same as expected	Pass
cQube_Regression_Semester_070	Check whether,total number of schools are equal or not / by click on blocks,clusters and schools	Total number of schools must be / equal by click on blocks, / clusters and schools	Same as expected	Pass
cQube_Regression_Semester_071	Check whether,total number of students are equal or not / by click on blocks,clusters and schools	Total number of students must be / equal by click on blocks,clusters / and schools	Same as expected	Pass
cQube_Regression_Semester_072	Check whether Block Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Semester_073	Check whether Cluster Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Semester_074	Check whether School Functionality is working or not	Map should be display and Points / Should be visible on map	Same as expected	Pass
cQube_Regression_Semester_075	Check whether Download Functionality is working or not	User Should able to see the / Downloaded File	Same as expected	Pass
cQube_Regression_Semester_076	Check whether Block level csv file is downloading or not	Block level csv file should be download	Same as expected	Pass
cQube_Regression_Semester_077	Check whether cluster level csv file is downloading or not	Cluster level csv file should be download	Same as expected	Pass
cQube_Regression_Semester_078	Check whether school level csv file is downloading or not	School level csv file should be download	Same as expected	Pass
cQube_Regression_Semester_079	Check whether Each District is selectable or not / From select box and also check whether Blocks-per-district-report is generating or not	Blocks-per-district csv file should be generated	Same as expected	Pass
cQube_Regression_Semester_080	Check whether Each block is selectable or not / From select box and also check whether Cluster_per_block_report is generating or not	Cluster_per_block_report csv file should be generated	Same as expected	Pass
cQube_Regression_Semester_081	Check whether Each cluster is selectable or not / From select box and also check whether School_per_cluster_report is generating or not	School_per_cluster_report csv file should be generated	Same as expected	Pass
cQube_Regression_Semester_082	Check whether Navigation Functionality / Is working or not	Navigation should happens / From cluster level to state level	Same as expected	Pass
cQube_Regression_Semester_083	Check whether Home icon is working or not	Districtwise map should be display	Same as expected	Pass
cQube_Regression_Semester_084	Check home button is working or not	Navigate to landing page	Same as expected	Pass
cQube_Regression_Semester_085	Check Dots are present on the map or not by selecting districts,block and clusters	Dots must be present	Same as expected	Pass
cQube_Regression_Semester_086	Check whether Logout Functionality / Is working or not	Login Page should be display	Same as expected	Pass
School infra map
cQube_Regression_Sc_Map_087	Check whether dashboad menu of cqube is working or not	Dashboard menu list to be display	Same as expected	Pass
cQube_Regression_Sc_Map_088	Check whether dashboad menu of School infrastructure is working or not	Navigate to School infrastructure Report	Same as expected	Pass
cQube_Regression_Sc_Map_089	Click on School infrastructure options , check weather options displayed or not	Options should be display	Same as expected	Pass
cQube_Regression_Sc_Map_090	Goto Dashboard , click on school infrastructure , and click on Report(map) , / Check weather is navigate to Report(map) or not	Navigate to Report(map) page should be display	Same as expected	Pass
cQube_Regression_Sc_Map_091	Check whether map is displayed or not / On the Semester Report	Map should be display	Same as expected	Pass
cQube_Regression_Sc_Map_092	Check whether Points are displayed or not / On the map	Points should be displayed on the map	Same as expected	Pass
cQube_Regression_Sc_Map_093	Click on Gujarat hyper link	It should be refresh school infrastructure page	Same as expected	Pass
cQube_Regression_Sc_Map_094	Click on Download icon and check weather csv file is downloading or not	Csv file is should be download	Same as expected	Pass
cQube_Regression_Sc_Map_095	Click on District select box and check weather select box contains options or / Not	District select box should be display list of districts	Same as expected	Pass
cQube_Regression_Sc_Map_096	Select any district from select box and click on download button to check it is / Downloading or not	Download the selected districtwise csv file	Same as expected	Pass
cQube_Regression_Sc_Map_097	Select any district from select box and select any block from select box / click on donwload button to check weather its downloading or not	Download the selected Blockwise csv file	Same as expected	Pass
cQube_Regression_Sc_Map_098	Select any district from select box and select any block from select box and / Select Cluster from select box ,click on donwload button to check weather it is / Downloading or not	Download the selected Clusterwise csv file	Same as expected	Pass
cQube_Regression_Sc_Map_099	Select any district from select box and click on Home icon check weather page / is Navigated to school_infrastructure page or not	Navigate back to school infrastructure home page	Same as expected	Pass
cQube_Regression_Sc_Map_100	Click on logout button	Navigate back to login page of cQube application	Same as expected	Pass
cQube_Regression_Sc_Map_101	Click on Catories select box , check weather cataory list is displaying or not	List of catagories to be display	Same as expected	Pass
cQube_Regression_Sc_Map_102	select any option from Infra_scores select box , check in map tooltip should / contains Selected option record	It should be display selected option record on tool tip of map	Same as expected	Pass
cQube_Regression_Sc_Map_103	Goto Infra_scores drop down and select as Infra_score	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_104	Goto Infra_scores drop down and select as Handwash_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_105	Goto Infra_scores drop down and select as Solar_panel_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_106	Goto Infra_scores drop down and select as Library_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_107	Goto Infra_scores drop down and select as Drinking_Water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_108	Goto Infra_scores drop down and select as Tap_water_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_109	Goto Infra_scores drop down and select as Hand_Pumps_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_110	Goto Infra_scores drop down and select as Electricity_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_111	Goto Infra_scores drop down and select as Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_112	Goto Infra_scores drop down and select as Boy’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_113	Goto Infra_scores drop down and select as Girl’s Toilet_Percentage	Map should be display selected Infra_score record	Same as expected	Pass
cQube_Regression_Sc_Map_114	Click on Blocks button , check weather block level map is displaying or not	Block level records should be display on map	Same as expected	Pass
cQube_Regression_Sc_Map_115	Click on Blocks button , check with footer informations	Block level footer information to be display	Same as expected	Pass
cQube_Regression_Sc_Map_116	Click on Cluster button , check with footer informations	Cluster level footer information to be display	Same as expected	Pass
cQube_Regression_Sc_Map_117	Click on Clusters button , and click on download button	Cluster level csv should be download	Same as expected	Pass
cQube_Regression_Sc_Map_118	Click on Schools button , check weather block level map is displaying or not	School level records should be display on map	Same as expected	Pass
cQube_Regression_Sc_Map_119	Click on Gujarath hyper link, Blocks, Clusters and Schools and check / Whether number of schools are equivalent in all the clicks" / Number of schools should be equal for / -Blocks / -Clusters / -Schools	Number of schools should be equal for each block , / Cluster and school	totol no of school value is different / in cluster level , compare to / blocks and schools	Resolved
cQube_Regression_Sc_Map_120	Select district from select box , and check with / downloading csv file , comapare footer values / with records in downloaded csv file	Both footer values and records in csv should be / equivalent	Same as expected	Pass
cQube_Regression_Sc_Map_121	Select district from select box , choose block from / select box , and check with downloading csv file , / comapare footer values with records in / downloaded csv file	Both footer values and records in csv should be / equivalent	Same as expected	Pass
cQube_Regression_Sc_Map_122	Select district from select box , choose block from / select box , choose cluster from select box and / check with downloading csv file , comapare footer / values with records in downloaded csv file	Both footer values and records in csv should be / equivalent	Same as expected	Pass
cQube_Regression_Sc_Map_123	Goto school infra map report , click on Blocks / button check with all infra scores options are / displaying or not on map	Block level infra scores records should be display	Same as expected	Pass
cQube_Regression_Sc_Map_124	Goto school infra map report , click on Clusters / button check with all infra scores options are / displaying or not on map	Cluster level infra scores records should be display	Same as expected	Pass
cQube_Regression_Sc_Map_125	Goto school infra map report , click on School / button check with all infra scores options are / displaying or not on map	School level infra scores records should be display	Same as expected	Pass
cQube_Regression_Sc_Map_126	choose any district . any block and cluster , check / with hyper link is working or not , modify like if click on / block hyper link cluster is goes off , if click on gujarath / navigate to districtwise home page	navigated back to districtiwise map page	Same as expected	Pass
School infra Report
cQube_Regression_Sc_Report_127	Check whether dashboad menu of cqube is working or not	Menu list should be Open	Same as expected	Pass
cQube_Regression_Sc_Report_128	Check whether dashboad menu of / School infrastructure report is working or not	School Infrastructure report for: Gujarat Should display	Same as expected	Pass
cQube_Regression_Sc_Report_129	Check page contains Graph and Tables	Graph and table should be display	Same as expected	Pass
cQube_Regression_Sc_Report_130	Select districtwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
cQube_Regression_Sc_Report_131	Select blockwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
cQube_Regression_Sc_Report_132	Select clusterwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
cQube_Regression_Sc_Report_133	Select schoolwise csv option from download report / from select box and click on donwload icon	It should download the selected / Download report csv	Same as expected	Pass
cQube_Regression_Sc_Report_134	Check hyperlinks are navigating back to the districtwise / crc report	Hyperlinks should navigate to the crc report	Same as expected	Pass
cQube_Regression_Sc_Report_135	check with home button is working or not	Navigate back to districtwise crc report / page	Same as expected	Pass
cQube_Regression_Sc_Report_136	Select district,block and click on home icon	Navigated to crc report	Same as expected	Pass
cQube_Regression_Sc_Report_137	Select district,block and cluster and click on home icon	Navigated to crc report	Same as expected	Pass
cQube_Regression_Sc_Report_138	Click on district name on the table and check whether / ascending and descending functionality is working or not	District name should be sorted based on the / input	Same as expected	Pass
cQube_Regression_Sc_Report_139	select district from select box ,click on download icon / check weather block level csv is downloading or not	Block level csv should be download	Same as expected	Pass
cQube_Regression_Sc_Report_140	Select district from select box ,select block from select / box ,click on download icon check weather cluster level / csv is downloading or not	Cluster level csv should be download	Same as expected	Pass
cQube_Regression_Sc_Report_141	Select district from select box ,select block from select / box ,select cluster from select box click on download / -icon check weather school level csv is downloading or not	School level csv should be download	Same as expected	Pass
cQube_Regression_Sc_Report_142	Select district from select box , select block from select box / and select cluster from select box and check with table / data is loading or not	School level table data should be display	Some of cluster table data / showing no data found	Resolved
cQube_Regression_Sc_Report_143	Select district from select box , select block from select box / and check with table data is loading or not	Cluster level table data should be display	Same as expected	Pass
cQube_Regression_Sc_Report_144	Select district from select box , check with table data is / loading or not	Block level table data should be display	Same as expected	Pass
cQube_Regression_Sc_Report_145	Check district wise table data and check with metric / percentages	Average metrics percentage should be / below or equal 100%	Same as expected	Pass
cQube_Regression_Sc_Report_146	Check District wise select box and check weather / district names are in order wise or not	District names should be in orderwise	Same as expected	Pass
cQube_Regression_Sc_Report_147	Check on crc report and click on logout	Login page should be displayed	Same as expected	Pass
cQube_Regression_Sc_Report_148	Check xaxis select box and check options are present / or not	X axis options should be display	Same as expected	Pass
cQube_Regression_Sc_Report_149	Check yaxis select box and check options are present / or not	Y axis options should be display	Same as expected	Pass
cQube_Regression_Sc_Report_150	Select district from select box ,select block from select / box and select cluster from select box and check with / download csv file and comapare csv file data with / table records	Both csv file records and table data should be / equivalent	Same as expected	Pass

## Smoke Testing
Project Name	cQube 1.1
Test Case Name	Smoke_Testcases
Created By	Chetan & Devaraj
Creation Date	7/16/2020
Reviewed By	Srinivas N & Radhika
Reviewed Date

Test Case ID	Test Case Description	Expected Result	Actual Result	Status
Automation Testcases
Login_to_cQube
Smoke_Tc_001	Check login functionality is working or not	Login to cqube application	Same as expected	Pass
Landing Page
Smoke_Tc_002	Click on student attendance report icon and check / weather navigated to student attendance report or / not	Navigate to student attendance home page	Same as expected	Pass
Smoke_Tc_003	Click on crc report icon and check / weather navigated to crc report or / not	Navigate to crc report home page	Same as expected	Pass
Smoke_Tc_004	Click on semester report icon and check / weather navigated to semester report or / not	Navigate to semester report home page	Same as expected	Pass
Smoke_Tc_005	Click on teacher attendance report icon and check / weather navigated to teacher attendance report or / not	Navigate to teacher attendance coming soon / page	Same as expected	Pass
Smoke_Tc_006	Click on school infrastrure map report icon and / check weather navigated to school infrastructure / map report or not	Navigate to school infrastrure map report / home page	Same as expected	Pass
Smoke_Tc_007	Click on school infrastrure scattor report icon and / check weather navigated to school infrastructure / scattor report or not	Navigate to school infrastrure scattor report / home page	Same as expected	Pass
Student Attendance Report
Smoke_Tc_008	Click on dash and click on student attedance report , / check weather student attendance landing page is / displayeed or not	Student attendance report landing / page should be display	Same as expected	Pass
Smoke_Tc_009	Check weather block button functionality is working or not	Block button functionality should be / work	Same as expected	Pass
Smoke_Tc_010	Check weather cluster button functionality is working or not	Cluster button functionality should be / work	Same as expected	Pass
Smoke_Tc_011	Check weather school button functionality is working or not	School button functionality should be / work	Same as expected	Pass
Smoke_Tc_012	Choose district from select box , check weather district is / selectable or not	District should be selectable from select / box	Same as expected	Pass
Smoke_Tc_013	Choose district from select box , choose block from select box / check weather block is selectable or not	Block should be selectable from select / box	Same as expected	Pass
Smoke_Tc_014	Choose district from select box , choose block from select box / and select cluster from select box ,check weather cluster is / selectable or not	Cluster should be selectable from select / box	Same as expected	Pass
Smoke_Tc_015	Click on hyper link , check weather it is working or not	Hyper link should be work	Same as expected	Pass
Smoke_Tc_016	Click on blocks , cluster and school button and check each / contains equivalent no of school record	No of schools record should be same	Same as expected	Pass
Smoke_Tc_017	Click on blocks , cluster and school button and check each / contains equivalent no of students record	No of students record should be same	Same as expected	Pass
Smoke_Tc_018	Check with download icon is working or not	Download functionality should be work	Same as expected	Pass
Smoke_Tc_019	Click on home icon , check weather it is working or not	Home icon should be work	Same as expected	Pass
Smoke_Tc_020	Check year select box and month wise select box , / options are selectable or not	Both functinalities should be work	Same as expected	Pass
Smoke_Tc_021	Check markers present on map or not	Markers should be display on map	Same as expected	Pass
Smoke_Tc_022	Check logout functionality is working or not	Logout should be work	Same as expected	Pass
CRC Report				Pass
Smoke_Tc_023	Click on CRC report on dashboard , check weather navigate / to crc report landing page or not	Navigated to crc report landing page	Same as expected	Pass
Smoke_Tc_024	Check x axis and y axis select box and check each options / are selectable or not	Both x and y axis options should be / selectable	Same as expected	Pass
Smoke_Tc_025	Check hyper link is working or not	Hyper link should be work	Same as expected	Pass
Smoke_Tc_026	Choose district from select box , check weather district is / selectable or not	District should be selectable from select / box	Same as expected	Pass
Smoke_Tc_027	Choose district from select box , choose block from select box / check weather block is selectable or not	Block should be selectable from select / box	Same as expected	Pass
Smoke_Tc_028	Choose district from select box , choose block from select box / and select cluster from select box ,check weather cluster is / selectable or not	Cluster should be selectable from select / box	Same as expected	Pass
Smoke_Tc_029	Check with table data contains records or not and order of / the table data	Table should be display records	Same as expected	Pass
Smoke_Tc_030	Check with donwload report options are working or not	Download report options should be work	Same as expected	Pass
Smoke_Tc_031	Select districtwise report and click on donwload button	Districtwise csv should be download	Same as expected	Pass
Smoke_Tc_032	Select any district from select box and click on home icon / check weather home is working or not	Home button should be work	Same as expected	Pass
Smoke_Tc_033	Download districtwisecsv and compare Total Number of schools	Total no of school should be same	Same as expected	Pass
Smoke_Tc_034	Download districtwisecsv and compare Total Number of visits	Total Number of visits should be same	Same as expected	Pass
Smoke_Tc_035	Download districtwisecsv and compare Total schools visited	Total schools visited should be same	Same as expected	Pass
Smoke_Tc_036	Check logout button , weather is working or not	Logout should be work	Same as expected	Pass
Smoke_Tc_037			Same as expected	Pass
Smoke_Tc_038	Click on dashboard and click on Semester report , / check weather Semester landing page is / displayeed or not	Semester report landing / page should be display	Same as expected	Pass
Smoke_Tc_039	Check weather block button functionality is working or not	Block button functionality should be / work	Same as expected	Pass
Smoke_Tc_040	Check weather cluster button functionality is working or not	Cluster button functionality should be / work	Same as expected	Pass
Smoke_Tc_041	Check weather school button functionality is working or not	School button functionality should be / work	Same as expected	Pass
Smoke_Tc_042	Choose district from select box , check weather district is / selectable or not	District should be selectable from select / box	Same as expected	Pass
Smoke_Tc_043	Choose district from select box , choose block from select box / check weather block is selectable or not	Block should be selectable from select / box	Same as expected	Pass
Smoke_Tc_044	Choose district from select box , choose block from / select box and select cluster from select box ,check / weather cluster is selectable or not	Cluster should be selectable from select / box	Same as expected	Pass
Smoke_Tc_045	Click on hyper link , check weather it is working or not	Hyper link should be work	Same as expected	Pass
Smoke_Tc_046	Click on blocks , cluster and school button and check each / contains equivalent no of school record	No of schools record should be same	Same as expected	Pass
Smoke_Tc_047	Click on blocks , cluster and school button and check each / contains equivalent no of students record	No of students record should be same	Same as expected	Pass
Smoke_Tc_048	Check with download icon is working or not	Download functionality should be work	Same as expected	Pass
Smoke_Tc_049	Click on home icon , check weather it is working or not	Home icon should be work	Same as expected	Pass
Smoke_Tc_050	Check markers present on map or not	Markers should be display on map	Same as expected	Pass
Smoke_Tc_051	Check logout functionality is working or not	Logout should be work	Same as expected	Pass
School Infrastructure Map report				Pass
Smoke_Tc_052	Click on dashboard and click on school infra report , / click on Map based Report ,check weather map report / landing page is displayeed or not	School infra map based report landing / page should be display	Same as expected	Pass
Smoke_Tc_053	Check weather block button functionality is working or not	Block button functionality should be / work	Same as expected	Pass
Smoke_Tc_054	Check weather cluster button functionality is working or not	Cluster button functionality should be / work	Same as expected	Pass
Smoke_Tc_055	Check weather school button functionality is working or not	School button functionality should be / work	Same as expected	Pass
Smoke_Tc_056	Choose district from select box , check weather district is / selectable or not	District should be selectable from select / box	Same as expected	Pass
Smoke_Tc_057	Choose district from select box , choose block from select box / check weather block is selectable or not	Block should be selectable from select / box	Same as expected	Pass
Smoke_Tc_058	Choose district from select box , choose block from select box / and select cluster from select box ,check weather cluster is / selectable or not	Cluster should be selectable from select / box	Same as expected	Pass
Smoke_Tc_059	Click on hyper link , check weather it is working or not	Hyper link should be work	Same as expected	Pass
Smoke_Tc_060	Click on blocks , cluster and school button and check each / contains equivalent no of school record	No of schools record should be same	Same as expected	Pass
Smoke_Tc_061	Click on blocks , cluster and school button and check each / contains equivalent no of students record	No of students record should be same	Same as expected	Pass
Smoke_Tc_062	Check with download icon is working or not	Download functionality should be work	Same as expected	Pass
Smoke_Tc_063	Click on home icon , check weather it is working or not	Home icon should be work	Same as expected	Pass
Smoke_Tc_064	Check markers present on map or not	Markers should be display on map	Same as expected	Pass
Smoke_Tc_065	Check infra scores select box and check weather each options / are selectable or not	Infra scores options should be selectable	Same as expected	Pass
Smoke_Tc_066	Check logout functionality is working or not	Logout should be work	Same as expected	Pass
School Infra Scattor report			Same as expected
Smoke_Tc_067	Click on scool infra report on dashboard ,click on Repot , / check weather navigate to scattor report landing page or not	Navigated to school infra scattor report / landing page	Same as expected	Pass
Smoke_Tc_068	Check x axis and y axis select box and check each options / are selectable or not	Both x and y axis options should be / selectable	Same as expected	Pass
Smoke_Tc_069	Check hyper link is working or not	Hyper link should be work	Same as expected	Pass
Smoke_Tc_070	Choose district from select box , check weather district is / selectable or not	District should be selectable from select / box	Same as expected	Pass
Smoke_Tc_071	Choose district from select box , choose block from select box / and select cluster from select box ,check weather cluster is / selectable or not	Cluster should be selectable from select / box	Same as expected	Pass
Smoke_Tc_072	Check with table data contains records or not and order of / the table data	Table should be display records	Same as expected	Pass
Smoke_Tc_073	Check with donwload report options are working or not	Download report options should be work	Same as expected	Pass
Smoke_Tc_074	Select districtwise report and click on donwload button	Districtwise csv should be download	Same as expected	Pass
Smoke_Tc_075	Select any district from select box and click on home icon / check weather home is working or not	Home button should be work	Same as expected	Pass
Smoke_Tc_076	Download districtwisecsv and compare Total schools visited	Total schools visited should be same	Same as expected	Pass